## BOQ
BILL OF QUANTITIES — project2
STOCK CODE | MATERIALS DESCRIPTION | QTY |  | RATE (PGK) | AMOUNT (PGK) | CONFIDENCE | SOURCE | NOTES / DRAWING REF
50106 - WPC (Timber)
| Timber Skirting ¦ 25 x 75 x 2400mm Timber | 88.3 | calculated |  |  | MEDIUM | ext_walls | Skirting = external wall interior face + both faces of internal partitions, minus door opening widths. Door gap deductions: ext_doors=0.920 m (DOOR_90×1); int_doors_×2f=8.000 m (DOOR_82×4, DOOR_72×1). Gross=97.2 m → net=88.3 m.
| Floor Finish ¦ (type by room) | 60.3 | calculated |  |  | MEDIUM | config room_schedule | Dry floor finish area from room schedule (5 rooms). Verandah (21.6 m²) excluded — has separate decking row. Verify room areas from architectural drawings.
| Floor Finish ¦ (type by room) | 4.5 | calculated |  |  | MEDIUM | config room_schedule | Wet floor finish (ceramic tile / non-slip) for wet areas: Toilet (4.50 m²). Verify with architect.
| Paint ¦ External, two coats | 92.16 | calculated |  |  | MEDIUM | dxf_geometry | Gross area; no deduction for openings.
| Paint ¦ Internal, two coats | 205.92 | calculated |  |  | MEDIUM | ceiling_area=64.80 m²; int_wal | Both faces of internal partitions included.
50107 - Structural & Base Steel & Footings
| FrameCAD Roof Panel ¦ LGS C89, 0.75BMT, G550, Z275 | 481.74 | measured |  |  | HIGH | framecad_bom
| FrameCAD Roof Truss ¦ LGS C89, 0.75BMT, G550, Z275 | 1634.29 | measured |  |  | HIGH | framecad_bom | QA NOTE: FrameCAD BOM 'Roof Trusses' tab total includes all roof structural members (truss chords, webs, purlin/rafter runs). This is the correct procurement quantity. An assembled-frame-count comparison will show a lower lm figure — the difference is expected and not a data error.
| FrameCAD Wall Frame ¦ LGS C89, all wall members | 2250.69 | measured |  |  | HIGH | framecad_bom
| FrameCAD Lintel ¦ LGS, lintel members | 3.57 | measured |  |  | HIGH | framecad_bom
| FrameCAD Wall Strap ¦ Diagonal strap brace | 49.73 | measured |  |  | HIGH | framecad_bom
| External Works ¦ Verandah Frame | 69.91 | measured |  |  | HIGH | ifc_model
| Steel Post ¦ 75 x 4mm SHS, Q345, HDG600 | 96.69 | measured |  |  | HIGH | ifc_model
| Roof Batten ¦ 41mm Top Hat, G550, Z275 | 1385.3 | measured |  |  | HIGH | framecad_bom | BOM total 266 pieces (1385.3 lm) — all batten zones. Grade split: ≥35mm (roof top-hat) = 85 nr / 510.0 lm; <35mm (ceiling/wall) = 181 nr / 875.3 lm. Zone separation inferred from BOM grade — see per-family rows below.
| Ceiling Batten ¦ G22 | 176 | measured |  |  | LOW | framecad_bom | Ceiling/wall batten (grade 22mm <35mm threshold). 4800mm stock length. Total: 844.8 lm. Zone inferred from grade — confirm against FrameCAD batten schedule.
| Ceiling Batten ¦ G22 | 5 | measured |  |  | LOW | framecad_bom | Ceiling/wall batten (grade 22mm <35mm threshold). 6100mm stock length. Total: 30.5 lm. Zone inferred from grade — confirm against FrameCAD batten schedule.
| Roof Batten ¦ 41mm Top Hat, G550, Z275 | 85 | measured |  |  | MEDIUM | framecad_bom | Roof top-hat batten (grade 40mm ≥35mm threshold). 6000mm stock length. Total: 510.0 lm. Zone inferred from grade — confirm against FrameCAD batten schedule.
| Floor Panel ¦ 1.8kPa Standard Load | 21 | inferred |  |  | LOW | project_config | MANUAL REVIEW REQUIRED. General pharmacy areas (waiting, consultation, staff, storage). 70% area estimate from building use. No FrameCAD floor tab available — obtain actual panel schedule from engineer. Panel dimensions assumed 600mm × 3600mm (2.16m² each).
| Floor Joist ¦ LGS C150, 1.8kPa Zone | 100.8 | inferred |  |  | LOW | project_config | MANUAL REVIEW REQUIRED. General pharmacy areas (waiting, consultation, staff, storage). 70% area estimate from building use. No FrameCAD floor tab available — obtain actual panel schedule from engineer. Joist count at 450mm spacing across 7.2m span, 9.0m run.
| Floor Bearer ¦ 1.8kPa Zone, pair | 3 | inferred |  |  | LOW | project_config | MANUAL REVIEW REQUIRED. General pharmacy areas (waiting, consultation, staff, storage). 70% area estimate from building use. No FrameCAD floor tab available — obtain actual panel schedule from engineer. Bearer pairs at 1800mm spacing. Verify from structural schedule.
| Floor Panel ¦ 4kPa High Load | 9 | inferred |  |  | LOW | project_config | MANUAL REVIEW REQUIRED. Dispensary area with heavy shelving/equipment. 30% area estimate. Obtain actual panel schedule from FrameCAD engineer before ordering. Panel dimensions assumed 600mm × 3600mm (2.16m² each).
| Floor Joist ¦ LGS C150, 4kPa Zone | 43.2 | inferred |  |  | LOW | project_config | MANUAL REVIEW REQUIRED. Dispensary area with heavy shelving/equipment. 30% area estimate. Obtain actual panel schedule from FrameCAD engineer before ordering. Joist count at 450mm spacing across 7.2m span, 9.0m run.
| Floor Bearer ¦ 4kPa Zone, pair | 2 | inferred |  |  | LOW | project_config | MANUAL REVIEW REQUIRED. Dispensary area with heavy shelving/equipment. 30% area estimate. Obtain actual panel schedule from FrameCAD engineer before ordering. Bearer pairs at 1800mm spacing. Verify from structural schedule.
| FC Sheet Floor ¦ 18mm thk, 1200 x 2400 Sheet | 24 | calculated |  |  | LOW | project_config+dxf_geometry | MANUAL REVIEW REQUIRED. Sheet size assumed same as ceiling FC sheet (1.2×2.4). Adjust if different.
| Fixing ¦ FC Floor Sheet Screw | 2 | calculated |  |  | LOW | project_config+dxf_geometry | 16 fixings per sheet; 200 per box.
| Substructure ¦ Strip Footing, External Perimeter | 38.4 | calculated |  |  | MEDIUM | derived_steel_floor | Strip footing assumed for steel floor frame bearing lines. Assumed 500 mm deep × 400 mm wide. Verify type and dimensions from structural drawings.
| Substructure ¦ Strip Footing Concrete Volume | 7.68 | calculated |  |  | LOW | derived_steel_floor | MANUAL REVIEW REQUIRED. Strip footing assumed for steel floor frame bearing lines. Assumed 500 mm deep × 400 mm wide. Verify type and dimensions from structural drawings.
| Substructure ¦ Strip Footing Formwork | 38.4 | calculated |  |  | MEDIUM | derived_steel_floor
| Substructure ¦ Bulk Earthworks / Level (provisional) | 0 | placeholder |  |  | LOW | no site survey in sources | MANUAL REVIEW REQUIRED. Excavation volume cannot be derived from architectural documents.
| Substructure ¦ Strip Footing, Internal Bearing | 29.4 | calculated |  |  | MEDIUM | dxf_geometry | Internal bearing lines assumed at each internal wall run. Total: 29.4 lm. Verify from structural drawings — actual bearing lines may differ from partition walls.
| Substructure ¦ Strip Footing, Internal Bearing | 5.88 | calculated |  |  | LOW | derived | MANUAL REVIEW REQUIRED. Assumed 500 mm deep × 400 mm wide. Verify.
| Substructure ¦ Pad Footing, Concrete | 15 | measured |  |  | MEDIUM | dxf_geometry
| Substructure ¦ Pad Footing Concrete Volume | 5.145 | calculated |  |  | LOW | derived | MANUAL REVIEW REQUIRED. Assumes 700×700×700 mm pads. Verify from structural engineer.
50111 - Fixings & Connectors
| Fixing ¦ 12G-14x20mm HEX Head, DP | 19 | calculated |  |  | MEDIUM | framecad_bom | MANUAL REVIEW REQUIRED. Stud-to-track connections: 2300.4lm × 4.0 per m = ~9202 screws, 19 boxes (500/box). Density: 2 screws per stud end (top+bottom). Verify with FrameCAD connection schedule.
| Fixing ¦ 10G-24x40mm Countersunk, DP | 3 | calculated |  |  | MEDIUM | framecad_bom | MANUAL REVIEW REQUIRED. Purlin-to-rafter / roof panel connections: 481.7lm × 3.0 per m = ~1445 screws, 3 boxes. Verify with FrameCAD connection report.
| Fixing ¦ 10G-14x16mm Wafer Head, DP | 7 | calculated |  |  | LOW | framecad_bom | MANUAL REVIEW REQUIRED. Batten-to-purlin connections: 1385.3lm total batten × 2.5 per m = ~3463. Includes roof, wall, and ceiling batten zones from FrameCAD BOM. Verify zone scope before ordering.
| Fixing ¦ M12 x 75mm Sleeve Anchor (Pad Footings) | 60 | calculated |  |  | MEDIUM | dxf_geometry | MANUAL REVIEW REQUIRED. 15 pad footings × 4 M12×75 anchors each (4-bolt base plate). Verify anchor embedment depth and edge distance from structural engineer.
| PH Bracket ¦ Post Holder (PHA/PHB/PHD) | 28 | calculated |  |  | LOW | ifc_model | MANUAL REVIEW REQUIRED. Post holder brackets at column bases. Count estimated from IFC steel post lm. Verify bracket type (PHA/PHB/PHD) against post size and load from structural drawings.
| Accessories ¦ Triple Grip Connector (Pryda) | 36 | calculated |  |  | LOW | dxf_geometry | MANUAL REVIEW REQUIRED. Roof-to-wall-plate cyclonic uplift connections at 1.2m centres along 42.4m eave line = 36 nr. Verify spacing and type from structural engineer (cyclone region requirement).
| Accessories ¦ Hold Down Washer, Cyclonic | 60 | calculated |  |  | LOW | dxf_geometry | MANUAL REVIEW REQUIRED. Hold-down washers at post base connections. 15 pads × 4 = 60 nr. Verify washer specification (size, grade) from structural drawings.
| Accessories ¦ Fix Plate Connector, G350 | 18 | calculated |  |  | LOW | framecad_bom | MANUAL REVIEW REQUIRED. Fix plates at strap bracing termination points: 49.7lm × 0.35 = 18 nr. Verify against FrameCAD connection schedule.
| Accessories ¦ Strap Brace Tensioner | 34 | calculated |  |  | LOW | framecad_bom | MANUAL REVIEW REQUIRED. Strap termination anchors: 49.7lm ÷ 3m avg run = 17 runs × 2 ends. Verify strap count and anchor type from FrameCAD connection schedule.
| Accessories ¦ Grommet 35mm Dia | 45 | inferred |  |  | LOW | dxf_geometry | MANUAL REVIEW REQUIRED. Cable/conduit grommets at LGS stud penetrations. 29.4m internal wall × 1.5 per m = 45 nr. Quantity depends on electrical/hydraulic layout. Verify from services drawings.
| Fixing ¦ Structural Fixings Remainder (PLACEHOLDER) | 0 | placeholder |  |  | LOW | no fixing schedule in source d | MANUAL REVIEW REQUIRED. PLACEHOLDER for connection schedule items not derivable from member lm alone. Typical items: M10/M12/M16 hex bolts (hold-down posts), angle brackets (knee bracing, ridge connections), spring washers, nyloc nuts. Obtain FrameCAD connection report for full schedule. Reference BOQ includes 256+ individual fixing line items — this row represents residual scope.
50112 - Roof & Roof Plumbing
| Insulation ¦ Sisalation / Sarking | 2 | calculated |  |  | HIGH | dxf_geometry
| Fixing ¦ Roof Tek Screw, Hex Head, DP | 11 | calculated |  |  | MEDIUM | dxf_geometry | 1 box per 10 m² (approx 250 screws/box at 25 screws/m²)
| Roof Cladding ¦ Custom Orb Corrugated CGI Sheet | 49 | calculated |  |  | MEDIUM | dxf_geometry | MANUAL REVIEW REQUIRED. run=2.51m (area/eaves) + 150mm lap → select 3.0m stock Verify sheet length and profile from spec.
| Ridge Cap ¦ Galvanised, lm | 10.6 | calculated |  |  | MEDIUM | dxf_geometry
| Fixing ¦ Ridge Cap Hex Head Screw | 36 | calculated |  |  | MEDIUM | dxf_geometry | 1 screw per 300 mm
| Ridge End Cap ¦ Galvanised | 2 | calculated |  |  | MEDIUM | dxf_geometry | 2 end caps per ridge run (one each end)
| Fascia Board ¦ Galvanised, lm | 42.4 | calculated |  |  | MEDIUM | dxf_geometry
| Fascia ¦ Clips | 71 | calculated |  |  | MEDIUM | dxf_geometry | 1 clip per 600 mm
| Accessories ¦ Birdproof Foam Strip | 42.4 | calculated |  |  | MEDIUM | dxf_geometry | runs full eaves length
| SL-14 ¦ PVC Box Gutter | 42.4 | calculated |  |  | MEDIUM | dxf_geometry
| SL-14 ¦ PVC Gutter Joiner | 3 | calculated |  |  | MEDIUM | dxf_geometry | PVC box gutter 6 m stock: joiners = total_lengths − estimated_run_count (≈eaves/10 m per run)
| SL-14 ¦ PVC Gutter Stop End | 6 | calculated |  |  | MEDIUM | dxf_geometry | 2 per run; add 2 per extra run > 20 m
| Barge Cap ¦ Galvanised, lm | 8.5 | calculated |  |  | LOW | dxf_geometry | MANUAL REVIEW REQUIRED.
| Barge End Cap ¦ Galvanised | 2 | calculated |  |  | LOW | dxf_geometry | MANUAL REVIEW REQUIRED. 2 end caps per barge run (ridge peak and eaves)
| SL-14 ¦ PVC Downpipe, 68mm | 6 | calculated |  |  | MEDIUM | dxf_geometry
| SL-14 ¦ PVC Gutter Drop Outlet | 6 | calculated |  |  | MEDIUM | dxf_geometry
| SL-14 ¦ PVC Downpipe Elbow, 90° | 12 | calculated |  |  | MEDIUM | dxf_geometry | top + bottom elbow per downpipe
| SL-14 ¦ PVC Downpipe Clip | 18 | calculated |  |  | MEDIUM | dxf_geometry | approx 3 clips per 3 m drop
50113 - External Cladding
| External Cladding ¦ FC Weatherboard | 87.14 | calculated |  |  | HIGH | dxf_geometry | Gross 92.16 m² − openings 5.02 m² = 87.14 m²
| External Cladding ¦ FC Weatherboard | 126 | calculated |  |  | MEDIUM | dxf_geometry | MANUAL REVIEW REQUIRED. Weatherboard: 200mm exposure, 4200mm stock length. Count includes 5% waste. Verify board profile and lap from spec.
| External Cladding ¦ FC Weatherboard | 72 | calculated |  |  | MEDIUM | dxf_geometry | H-joiners per façade face (joiners at butt-joins only, not corners). Verify count from cladding layout.
| External Cladding ¦ Corner Flashing, Galvanised | 4 | inferred |  |  | MEDIUM | dxf_geometry | Corner count from building geometry (L=12.0m × W=7.2m rectangular = 4 corners). Verify against floor plan.
| External Cladding ¦ Corner Trim / Angle Bead | 9.6 | calculated |  |  | MEDIUM | derived | One trim per corner, full wall height. Verify profile and spec.
| External Cladding ¦ FC Weatherboard | 768 | calculated |  |  | MEDIUM | dxf_geometry | Stud clips at 600mm centres. Verify clip type from manufacturer spec.
| Fixing ¦ Stainless Steel Screw (Cladding) | 1536 | calculated |  |  | LOW | derived from clip count | 2 × stainless screws per fixing clip. Verify size and type from spec.
| Accessories ¦ Building Wrap / Sarking | 96.77 | calculated |  |  | MEDIUM | dxf_geometry | Includes 5% for laps. Gross area — no deduction for openings in sarking schedule.
| External Works ¦ Verandah Decking | 21.6 | measured |  |  | HIGH | dxf_geometry
| Substructure ¦ Site Preparation (Provisional) | 0 | placeholder |  |  | LOW | no site survey in sources | MANUAL REVIEW REQUIRED. Site preparation scope cannot be derived from drawings. Confirm with engineer.
50114 - Openings
| Door ¦ 920mm Wide (DOOR_90) | 1 | measured |  |  | HIGH | dxf_blocks | swing=hinged
| Door ¦ 820mm Wide (DOOR_82) | 4 | measured |  |  | HIGH | dxf_blocks | swing=hinged
| Door ¦ 720mm Wide (DOOR_72) | 1 | measured |  |  | HIGH | dxf_blocks | swing=hinged
| Flashing ¦ Door Head, Galvanised | 5.52 | calculated |  |  | MEDIUM | dxf_blocks | Head flashing extends 50 mm beyond door frame each side.
| Flashing ¦ Door Sill, Galvanised | 5.52 | calculated |  |  | MEDIUM | dxf_blocks | Sill flashing for all doors. Remove from internal doors not requiring sill.
| Door ¦ Leaf | 1 | calculated |  |  | HIGH | dxf_blocks | opening_mark=DOOR_90
| Door ¦ Frame Set | 1 | calculated |  |  | HIGH | dxf_blocks | opening_mark=DOOR_90
| Door ¦ Hinge (pair) | 3 | calculated |  |  | MEDIUM | dxf_blocks | opening_mark=DOOR_90 3 pairs per door (standard)
| Door ¦ Lockset | 1 | calculated |  |  | HIGH | dxf_blocks | opening_mark=DOOR_90
| Door ¦ Stop | 1 | calculated |  |  | HIGH | dxf_blocks | opening_mark=DOOR_90
| Door ¦ Leaf | 4 | calculated |  |  | HIGH | dxf_blocks | opening_mark=DOOR_82
| Door ¦ Frame Set | 4 | calculated |  |  | HIGH | dxf_blocks | opening_mark=DOOR_82
| Door ¦ Hinge (pair) | 12 | calculated |  |  | MEDIUM | dxf_blocks | opening_mark=DOOR_82 3 pairs per door (standard)
| Door ¦ Lockset | 4 | calculated |  |  | HIGH | dxf_blocks | opening_mark=DOOR_82
| Door ¦ Stop | 4 | calculated |  |  | HIGH | dxf_blocks | opening_mark=DOOR_82
| Door ¦ Leaf | 1 | calculated |  |  | HIGH | dxf_blocks | opening_mark=DOOR_72
| Door ¦ Frame Set | 1 | calculated |  |  | HIGH | dxf_blocks | opening_mark=DOOR_72
| Door ¦ Hinge (pair) | 3 | calculated |  |  | MEDIUM | dxf_blocks | opening_mark=DOOR_72 3 pairs per door (standard)
| Door ¦ Lockset | 1 | calculated |  |  | HIGH | dxf_blocks | opening_mark=DOOR_72
| Door ¦ Stop | 1 | calculated |  |  | HIGH | dxf_blocks | opening_mark=DOOR_72
| Window ¦ Louvre, 1100mm Wide | 8 | measured |  |  | MEDIUM | dxf_blocks | type=louvre
| Window ¦ Louvre, 800mm Wide | 2 | measured |  |  | MEDIUM | dxf_blocks | type=louvre
| Window ¦ Louvre, 1800mm Wide | 1 | measured |  |  | MEDIUM | dxf_blocks | type=louvre
| Flashing ¦ Window Head, Galvanised | 9.44 | calculated |  |  | MEDIUM | dxf_blocks | Head flashing extends 50 mm beyond frame each side.
| Flashing ¦ Window Sill, Galvanised | 9.44 | calculated |  |  | MEDIUM | dxf_blocks | Sill flashing same lm as head flashing. Remove if window sits on masonry sill.
| Window ¦ Louvre Blade, 1100mm Wide | 64 | calculated |  |  | LOW | dxf_blocks | MANUAL REVIEW REQUIRED. Frame height 750 mm (config_default=750mm). 8 blades per frame at 100 mm pitch. Verify blade count and size from window schedule.
| Flashing ¦ Window Head, Galvanised | 1.8 | calculated |  |  | MEDIUM | dxf_blocks | Head flashing extends 50 mm beyond frame each side.
| Flashing ¦ Window Sill, Galvanised | 1.8 | calculated |  |  | MEDIUM | dxf_blocks | Sill flashing same lm as head flashing. Remove if window sits on masonry sill.
| Window ¦ Louvre Blade, 800mm Wide | 16 | calculated |  |  | LOW | dxf_blocks | MANUAL REVIEW REQUIRED. Frame height 750 mm (config_default=750mm). 8 blades per frame at 100 mm pitch. Verify blade count and size from window schedule.
| Flashing ¦ Window Head, Galvanised | 1.95 | calculated |  |  | MEDIUM | dxf_blocks | Head flashing extends 50 mm beyond frame each side.
| Flashing ¦ Window Sill, Galvanised | 1.95 | calculated |  |  | MEDIUM | dxf_blocks | Sill flashing same lm as head flashing. Remove if window sits on masonry sill.
| Window ¦ Louvre Blade, 1800mm Wide | 8 | calculated |  |  | LOW | dxf_blocks | MANUAL REVIEW REQUIRED. Frame height 750 mm (config_default=750mm). 8 blades per frame at 100 mm pitch. Verify blade count and size from window schedule.
| Window ¦ Louvre Frame | 8 | calculated |  |  | MEDIUM | dxf_blocks | opening_mark=WINDOW_LOUVRE_1100
| Window ¦ Louvre Blade | 8 | calculated |  |  | MEDIUM | dxf_blocks | opening_mark=WINDOW_LOUVRE_1100
| Window ¦ Fly Screen | 8 | calculated |  |  | MEDIUM | dxf_blocks | opening_mark=WINDOW_LOUVRE_1100
| Window ¦ Louvre Frame | 2 | calculated |  |  | MEDIUM | dxf_blocks | opening_mark=WINDOW_LOUVRE_800
| Window ¦ Louvre Blade | 2 | calculated |  |  | MEDIUM | dxf_blocks | opening_mark=WINDOW_LOUVRE_800
| Window ¦ Fly Screen | 2 | calculated |  |  | MEDIUM | dxf_blocks | opening_mark=WINDOW_LOUVRE_800
| Window ¦ Louvre Frame | 1 | calculated |  |  | MEDIUM | dxf_blocks | opening_mark=WINDOW_LOUVRE_1800
| Window ¦ Louvre Blade | 1 | calculated |  |  | MEDIUM | dxf_blocks | opening_mark=WINDOW_LOUVRE_1800
| Window ¦ Fly Screen | 1 | calculated |  |  | MEDIUM | dxf_blocks | opening_mark=WINDOW_LOUVRE_1800
| Window ¦ Fly Screen, 1100mm Wide | 6.48 | calculated |  |  | LOW | dxf_blocks | MANUAL REVIEW REQUIRED. Fly screen for louvre window WINDOW_LOUVRE_1100 (8 nr). Area: 1.08m × 0.750m = 0.810 m² each. Tropical building — all louvre openings require insect screening. Verify frame height from window schedule.
| Window ¦ Fly Screen, 800mm Wide | 1.2 | calculated |  |  | LOW | dxf_blocks | MANUAL REVIEW REQUIRED. Fly screen for louvre window WINDOW_LOUVRE_800 (2 nr). Area: 0.80m × 0.750m = 0.599 m² each. Tropical building — all louvre openings require insect screening. Verify frame height from window schedule.
| Window ¦ Fly Screen, 1800mm Wide | 1.39 | calculated |  |  | LOW | dxf_blocks | MANUAL REVIEW REQUIRED. Fly screen for louvre window WINDOW_LOUVRE_1800 (1 nr). Area: 1.85m × 0.750m = 1.385 m² each. Tropical building — all louvre openings require insect screening. Verify frame height from window schedule.
| Door ¦ Closer, Hydraulic | 1 | inferred |  |  | MEDIUM | dxf_blocks | MANUAL REVIEW REQUIRED. Door closer inferred for pharmacy entrance doors. Marks: DOOR_90 (1 nr). Verify which doors require closers from door schedule and architect. Commercial pharmacy may require controlled entry.
| Timber Architrave ¦ 12 x 75 x 2400mm Timber | 36 | calculated |  |  | MEDIUM | derived from door_count=6
| Timber Architrave ¦ 12 x 75 x 2400mm Timber | 52.8 | calculated |  |  | MEDIUM | derived from window_count=11
50115 - Internal Linings & Ceilings
| External Lining ¦ FC Sheet, 1200 x 2400mm | 27 | calculated |  |  | MEDIUM | dxf_geometry | Opening deductions: doors=1.877 m² [DOOR_90×1(0.920×2.04)]; windows=9.064 m² [WINDOW_LOUVRE_1100×8(1.080×0.75), WINDOW_LOUVRE_800×2(0.799×0.75), WINDOW_LOUVRE_1800×1(1.847×0.75)] (louvre height=0.75 m from config default). Gross=92.16 m² − 10.941 m² = net=81.22 m².
| Fixing ¦ FC Sheet Screw (External) | 11 | calculated |  |  | LOW | derived from ext_wall_area_net
| Internal Lining ¦ FC Sheet, 1200 x 2400mm | 41 | calculated |  |  | HIGH | dxf_geometry | Opening deductions (assumed-internal doors, both partition faces): 16.320 m² [DOOR_82×4×2f(0.820×2.04), DOOR_72×1×2f(0.720×2.04)]. Gross=141.12 m² − 16.320 m² = net=124.80 m². Doors classified as internal by width < 0.85 m threshold. Measured from DXF WALLS layer: 8 internal wall runs.
| Fixing ¦ FC Sheet Screw (Internal) | 16 | calculated |  |  | LOW | derived from int_wall_area_bot | Opening deductions (assumed-internal doors, both partition faces): 16.320 m² [DOOR_82×4×2f(0.820×2.04), DOOR_72×1×2f(0.720×2.04)]. Gross=141.12 m² − 16.320 m² = net=124.80 m². Doors classified as internal by width < 0.85 m threshold. Measured from DXF WALLS layer: 8 internal wall runs.
| Internal Lining Accessory ¦ PVC H Joiner | 117.6 | calculated |  |  | LOW | dxf_geometry | 1 vertical joiner strip per 1.2 m sheet-width run × 2.4 m height.
| Internal Lining ¦ Waterproof Board / FC, Wet Area | 7 | inferred |  |  | LOW | rooms=['Toilet'] | MANUAL REVIEW REQUIRED. Wet area lining derived from room perimeter estimate. Verify room dimensions.
| Ceiling Lining ¦ FC Sheet, 1200 x 2400mm | 24 | calculated |  |  | MEDIUM | derived
| Ceiling Batten ¦ G22 | 162 | calculated |  |  | MEDIUM | derived
| Fixing ¦ FC Sheet Screw (Ceiling) | 7 | calculated |  |  | LOW | derived from ceiling_area=64.8
| Verandah Soffit Lining — FC Sheet (6mm, 1200×2400) | 8 | calculated |  |  | HIGH | dxf_geometry | Verandah soffit lining: 21.60 m² from DXF verandah polygon. Soffit area treated equal to verandah floor area. Verify from architectural drawings.
| Verandah Soffit Batten (LGS / timber) | 54 | calculated |  |  | MEDIUM | dxf_geometry | Verandah soffit batten: 21.60 m² at 400 mm spacing = 54.0 lm.
| Timber Cornice ¦ 25 x 25 x 2400mm Timber | 38.4 | calculated |  |  | MEDIUM | dxf_geometry | Assumes cornice on external walls only. Add int_wall_lm if cornice on internal walls too.
50117 - Services (Hydraulics — Partial)
| Hydraulics ¦ Hand Basin | 1 | inferred |  |  | LOW | room_schedule | MANUAL REVIEW REQUIRED. Inferred from room type 'pharmacy'.
| Hydraulics ¦ Tapware | 1 | inferred |  |  | LOW | room_schedule | MANUAL REVIEW REQUIRED. Inferred from room type 'pharmacy'.
| Services ¦ Cold Room / Refrigeration (PLACEHOLDER) | 1 | inferred |  |  | LOW | room_schedule | MANUAL REVIEW REQUIRED. Inferred from room type 'pharmacy'.
| Services ¦ Builder's Works, Electrical | 1 | inferred |  |  | LOW | room_schedule | MANUAL REVIEW REQUIRED. Inferred from room type 'pharmacy'.
| Services ¦ Builder's Works, Services | 1 | inferred |  |  | LOW | room_schedule | MANUAL REVIEW REQUIRED. Inferred from room type 'waiting'.
| Hydraulics ¦ Hand Basin | 1 | inferred |  |  | LOW | room_schedule | MANUAL REVIEW REQUIRED. Inferred from room type 'consulting'.
| Hydraulics ¦ Tapware | 1 | inferred |  |  | LOW | room_schedule | MANUAL REVIEW REQUIRED. Inferred from room type 'consulting'.
| Hydraulics ¦ Builder's Works (Plumbing) | 1 | inferred |  |  | LOW | room_schedule | MANUAL REVIEW REQUIRED. Inferred from room type 'consulting'.
| Services ¦ Builder's Works, Electrical | 1 | inferred |  |  | LOW | room_schedule | MANUAL REVIEW REQUIRED. Inferred from room type 'office'.
| Hydraulics ¦ WC Pan (close-coupled) | 1 | inferred |  |  | MEDIUM | room_schedule | MANUAL REVIEW REQUIRED. Inferred from room type 'toilet'.
| Hydraulics ¦ WC Cistern | 1 | inferred |  |  | MEDIUM | room_schedule | MANUAL REVIEW REQUIRED. Inferred from room type 'toilet'.
| Hydraulics ¦ Hand Basin | 1 | inferred |  |  | MEDIUM | room_schedule | MANUAL REVIEW REQUIRED. Inferred from room type 'toilet'.
| Hydraulics ¦ Tapware | 1 | inferred |  |  | MEDIUM | room_schedule | MANUAL REVIEW REQUIRED. Inferred from room type 'toilet'.
| FFE ¦ Mirror | 1 | inferred |  |  | LOW | room_schedule | MANUAL REVIEW REQUIRED. Inferred from room type 'toilet'.
| FFE ¦ Toilet Roll Holder | 1 | inferred |  |  | LOW | room_schedule | MANUAL REVIEW REQUIRED. Inferred from room type 'toilet'.
| FFE ¦ Towel Rail | 1 | inferred |  |  | LOW | room_schedule | MANUAL REVIEW REQUIRED. Inferred from room type 'toilet'.
| Hydraulics ¦ Floor Waste | 1 | inferred |  |  | MEDIUM | room_schedule | MANUAL REVIEW REQUIRED. Inferred from room type 'toilet'.
| Hydraulics ¦ Builder's Works (Plumbing) | 1 | inferred |  |  | MEDIUM | room_schedule | MANUAL REVIEW REQUIRED. Inferred from room type 'toilet'.
| Hydraulics ¦ WC Pan | 15.3 | inferred |  |  | LOW | room | MANUAL REVIEW REQUIRED. Inferred: perimeter (8.5 m) × 1800 mm splash-zone height. No finish schedule in source documents. Verify tile type, height, and area from architectural drawings. Deduct openings.
| Hydraulics ¦ Wet Area Waterproofing Membrane | 5.78 | inferred |  |  | MEDIUM | room | MANUAL REVIEW REQUIRED. Waterproofing: floor area + 150 mm upstand on walls for Toilet. Verify room dimensions and upstand height from architectural drawings.
| Services ¦ Builder's Works, Services | 1 | inferred |  |  | LOW | room_schedule | MANUAL REVIEW REQUIRED. Inferred from room type 'store'.
| Services ¦ Air Conditioning / Mechanical (PLACEHOLDER) | 0 | placeholder |  |  | LOW | building_type=pharmacy | MANUAL REVIEW REQUIRED. PLACEHOLDER. Commercial building in tropical climate likely requires split-system or cassette AC units. No mechanical schedule or equipment schedule in source documents. Obtain from mechanical engineer or building services consultant. Include: outdoor units, indoor units, refrigerant pipework, electrical supply, condensate drainage, ceiling penetrations.
| Electrical ¦ Exhaust Fan | 0 | placeholder |  |  | LOW | building_type=pharmacy | MANUAL REVIEW REQUIRED. PLACEHOLDER. BCA F4.6 requires mechanical exhaust in rooms without openable windows. Confirm exhaust fan type, ducting, and external discharge location from architectural drawings.
| Electrical ¦ Main Switchboard / Distribution Board | 1 | inferred |  |  | LOW | floor_area=86.40 m² (building- | MANUAL REVIEW REQUIRED. 1 per building; adjust for sub-boards
| Hydraulics ¦ Main Water Meter / Stopcock | 1 | inferred |  |  | LOW | floor_area=86.40 m² (building- | MANUAL REVIEW REQUIRED. Whole-building service allowance.
| Hydraulics ¦ Hot Water System | 1 | inferred |  |  | LOW | floor_area=86.40 m² (building- | MANUAL REVIEW REQUIRED. only if not allocated to individual rooms
| Electrical ¦ Smoke Detector | 3 | inferred |  |  | LOW | floor_area=86.40 m² (building- | MANUAL REVIEW REQUIRED. 1 per 40 m² floor area (indicative)
50118 - Insulation
| Insulation ¦ Glasswool Batts, Roof / Ceiling | 106.6 | calculated |  |  | HIGH | dxf_geometry
| Insulation ¦ Glasswool Batts, External Wall | 92.16 | calculated |  |  | MEDIUM | dxf_geometry | Gross wall area; deduct large openings if required.
50124 - Stairs & Balustrades
| Stair ¦ Stringer | 1 | inferred |  |  | LOW | project_config | MANUAL REVIEW REQUIRED. Entry stair — riser count estimated from raised floor height (~525mm). Verify from architectural drawings.
| Stair ¦ Tread | 3 | inferred |  |  | LOW | project_config | MANUAL REVIEW REQUIRED.
| Stair ¦ Component | 2 | calculated |  |  | MEDIUM | project_config | 1 newel post at top and bottom of each flight.
| Balustrade ¦ Assembly | 0.75 | calculated |  |  | LOW | project_config | MANUAL REVIEW REQUIRED. Verify length from architectural drawings.
| Balustrade ¦ Post | 1 | calculated |  |  | LOW | project_config | MANUAL REVIEW REQUIRED. 1 post per 1.2 m spacing. Verify from balustrade schedule.
| Balustrade ¦ Assembly | 0.75 | inferred |  |  | LOW | project_config | MANUAL REVIEW REQUIRED. Infill height assumed 1.0 m. Adjust for guard height requirement (≥1.0 m at >1.0 m fall).
| Balustrade ¦ Handrail | 0.75 | calculated |  |  | LOW | project_config | MANUAL REVIEW REQUIRED. Verify handrail length. Continuous rail both sides of flight where required by code.
| Access Ramp ¦ Surface, Concrete / Non-slip | 8.82 | inferred |  |  | LOW | derived from project_config | MANUAL REVIEW REQUIRED. Access ramp: 1:14 gradient, stair: 3 risers × 175 mm = 525 mm → 7.35 m run × 1.2 m wide = 8.82 m². Verify need and exact dimensions from architectural drawings and BCA D3.3.
| Access Ramp ¦ (type by design) | 14.7 | inferred |  |  | LOW | derived from ramp run | MANUAL REVIEW REQUIRED. Continuous handrails both sides of ramp. Verify height and spec from architectural drawings.
| Access Ramp ¦ Edge Kerb / Guard | 14.7 | inferred |  |  | LOW | derived from ramp run | MANUAL REVIEW REQUIRED. Kerb guard (min 75 mm high) both sides. Verify from architectural drawings.
| Balustrade ¦ Assembly | 20.4 | measured |  |  | HIGH | dxf_geometry
| Balustrade ¦ Handrail | 20.4 | calculated |  |  | MEDIUM | dxf_geometry | Reduce if one side abuts building wall.
| Balustrade ¦ Post | 17 | calculated |  |  | LOW | derived from verandah_perimete

## Traceability
Item No | Package Code | Section (Final BOQ) | Item Name (Original) | Item Display Name | Unit | Qty | Status | Quantity Basis | Source Evidence | Derivation Rule | Confidence
F01 | 50106 | 50106 - WPC (Timber) | Skirting Board | Timber Skirting ¦ 25 x 75 x 2400mm Timber | lm | 88.3 | calculated | ext_wall_lm(38.4) + int_wall_lm×2(29.4×2) − door_gaps(0.92+8.00) | ext_walls: 38.40 m [dxf_geometry]; int_walls: 29.40 m [dxf_geometry] | ext_wall_perimeter + int_wall_lm × 2 − door_widths | MEDIUM
F04 | 50106 | 50106 - WPC (Timber) | Floor Finish — Dry Area (vinyl plank / screed) | Floor Finish ¦ (type by room) | m2 | 60.3 | calculated | sum(dry room areas from room_schedule) | config room_schedule: Dispensary, Waiting / Reception, Consultation Room, Staff Room, Storage = 60.30 m² (enclosed=64.80 m²) | sum(room_area for non-wet rooms) | MEDIUM
F05 | 50106 | 50106 - WPC (Timber) | Floor Finish — Wet Area (ceramic tile) | Floor Finish ¦ (type by room) | m2 | 4.5 | calculated | sum(wet room areas from room_schedule) | config room_schedule: Toilet = 4.50 m² | sum(room_area for wet rooms) | MEDIUM
F06 | 50106 | 50106 - WPC (Timber) | Paint — External | Paint ¦ External, two coats | m2 | 92.16 | calculated | ext_wall_perimeter × wall_height | dxf_geometry: ext_wall_lm=38.40 × h=2.4 | 38.40 × 2.4 | MEDIUM
F07 | 50106 | 50106 - WPC (Timber) | Paint — Internal | Paint ¦ Internal, two coats | m2 | 205.92 | calculated | ceiling_area(64.80) + int_wall_both_faces(141.12) | ceiling_area=64.80 m²; int_wall_lm=29.40 m × 2 faces [dxf_geometry] | ceiling_area + sum(int_wall.area_m2) [area_m2 = lm × h × 2 faces] | MEDIUM
A01 | 50107 | 50107 - Structural & Base Steel & Footings | Roof Panel Frame (purlin / roof panel 89S41) | FrameCAD Roof Panel ¦ LGS C89, 0.75BMT, G550, Z275 | lm | 481.74 | measured | direct from framecad_bom | framecad_bom: Tab Roof Panels | direct from source | HIGH
A02 | 50107 | 50107 - Structural & Base Steel & Footings | Roof Truss Frame (truss chord + web 89S41) | FrameCAD Roof Truss ¦ LGS C89, 0.75BMT, G550, Z275 | lm | 1634.29 | measured | direct from framecad_bom | framecad_bom: Tab Roof Trusses | direct from source | HIGH
A03 | 50107 | 50107 - Structural & Base Steel & Footings | Wall Frame — all wall members 89S41 | FrameCAD Wall Frame ¦ LGS C89, all wall members | lm | 2250.69 | measured | direct from framecad_bom | framecad_bom: Tab Wall Panels | direct from source | HIGH
A04 | 50107 | 50107 - Structural & Base Steel & Footings | Wall Frame — lintel 150×32×0.95 | FrameCAD Lintel ¦ LGS, lintel members | lm | 3.57 | measured | direct from framecad_bom | framecad_bom: Lintel entries | direct from source | HIGH
A05 | 50107 | 50107 - Structural & Base Steel & Footings | Wall Frame — diagonal strap 32×0.95 | FrameCAD Wall Strap ¦ Diagonal strap brace | lm | 49.73 | measured | direct from framecad_bom | framecad_bom: Strap entries | direct from source | HIGH
A06 | 50107 | 50107 - Structural & Base Steel & Footings | Verandah Frame — 89S41 | External Works ¦ Verandah Frame | lm | 69.91 | measured | direct from ifc_model | ifc_model: V1/verandah members | direct from source | HIGH
A07 | 50107 | 50107 - Structural & Base Steel & Footings | Structural Steel Post (75×75×4 SHS) | Steel Post ¦ 75 x 4mm SHS, Q345, HDG600 | lm | 96.69 | measured | direct from ifc_model | ifc_model: SHS steel | direct from source | HIGH
A08 | 50107 | 50107 - Structural & Base Steel & Footings | Roof Battens (FRAMECAD BATTEN — all zones) | Roof Batten ¦ 41mm Top Hat, G550, Z275 | lm | 1385.3 | measured | framecad_bom: BATTEN schedule total | framecad_bom: FrameCAD BATTEN entries | direct from BOM | HIGH
A09 | 50107 | 50107 - Structural & Base Steel & Footings | Ceiling/Wall Batten G22 × 4800mm | Ceiling Batten ¦ G22 | nr | 176 | measured | framecad_bom: 176 × 4800mm = 844.8 lm | framecad_bom: BATTEN 22 176 4800 | 176 nr × 4800mm | LOW
A10 | 50107 | 50107 - Structural & Base Steel & Footings | Ceiling/Wall Batten G22 × 6100mm | Ceiling Batten ¦ G22 | nr | 5 | measured | framecad_bom: 5 × 6100mm = 30.5 lm | framecad_bom: BATTEN 22 5 6100 | 5 nr × 6100mm | LOW
A11 | 50107 | 50107 - Structural & Base Steel & Footings | Roof Top-Hat Batten G40 × 6000mm | Roof Batten ¦ 41mm Top Hat, G550, Z275 | nr | 85 | measured | framecad_bom: 85 × 6000mm = 510.0 lm | framecad_bom: BATTEN 40 85 6000 | 85 nr × 6000mm | MEDIUM
G01 | 50107 | 50107 - Structural & Base Steel & Footings | Floor Panel — Standard Load Floor Panel — General Areas (1.8kPa) | Floor Panel ¦ 1.8kPa Standard Load | nr | 21 | inferred | project_config: main_floor_area(64.8m²) × 0.7 fraction ÷ panel_area(2.16m²) | project_config: main_floor_area=64.80m² × fraction(0.7) = 45.36m²; joist_spacing=450mm; bearer_spacing=1800mm; span=dxf_geometry: DXF: floor=86.4m² perim=38.4m → L=12.0m W=7.2m; verandah=21.6m² depth=3.0m (engineering inference: full-width attachment); main=64.8m² (9.0m×7.2m); span=7.2m run=9.0m | ceil(45.36 / 2.16) | LOW
G02 | 50107 | 50107 - Structural & Base Steel & Footings | Floor Joist LGS — 1.8kPa Zone | Floor Joist ¦ LGS C150, 1.8kPa Zone | lm | 100.8 | inferred | project_config: joist_rows(16) × run(9.0m) × fraction(0.7) | project_config: main_floor_area=64.80m² × fraction(0.7) = 45.36m²; joist_spacing=450mm; bearer_spacing=1800mm; span=dxf_geometry: DXF: floor=86.4m² perim=38.4m → L=12.0m W=7.2m; verandah=21.6m² depth=3.0m (engineering inference: full-width attachment); main=64.8m² (9.0m×7.2m); span=7.2m run=9.0m | ceil(span/0.45) × run × fraction | LOW
G03 | 50107 | 50107 - Structural & Base Steel & Footings | Floor Bearer (pair) — 1.8kPa Zone | Floor Bearer ¦ 1.8kPa Zone, pair | nr | 3 | inferred | project_config: ceil(span_short(7.2m) / bearer_spacing(1.8m) × fraction(0.7)) | project_config: main_floor_area=64.80m² × fraction(0.7) = 45.36m²; joist_spacing=450mm; bearer_spacing=1800mm; span=dxf_geometry: DXF: floor=86.4m² perim=38.4m → L=12.0m W=7.2m; verandah=21.6m² depth=3.0m (engineering inference: full-width attachment); main=64.8m² (9.0m×7.2m); span=7.2m run=9.0m | ceil(7.2/1.8 × 0.7) | LOW
G04 | 50107 | 50107 - Structural & Base Steel & Footings | Floor Panel — High-Load Floor Panel — Dispensary (4kPa) | Floor Panel ¦ 4kPa High Load | nr | 9 | inferred | project_config: main_floor_area(64.8m²) × 0.3 fraction ÷ panel_area(2.16m²) | project_config: main_floor_area=64.80m² × fraction(0.3) = 19.44m²; joist_spacing=450mm; bearer_spacing=1800mm; span=dxf_geometry: DXF: floor=86.4m² perim=38.4m → L=12.0m W=7.2m; verandah=21.6m² depth=3.0m (engineering inference: full-width attachment); main=64.8m² (9.0m×7.2m); span=7.2m run=9.0m | ceil(19.44 / 2.16) | LOW
G05 | 50107 | 50107 - Structural & Base Steel & Footings | Floor Joist LGS — 4kPa Zone | Floor Joist ¦ LGS C150, 4kPa Zone | lm | 43.2 | inferred | project_config: joist_rows(16) × run(9.0m) × fraction(0.3) | project_config: main_floor_area=64.80m² × fraction(0.3) = 19.44m²; joist_spacing=450mm; bearer_spacing=1800mm; span=dxf_geometry: DXF: floor=86.4m² perim=38.4m → L=12.0m W=7.2m; verandah=21.6m² depth=3.0m (engineering inference: full-width attachment); main=64.8m² (9.0m×7.2m); span=7.2m run=9.0m | ceil(span/0.45) × run × fraction | LOW
G06 | 50107 | 50107 - Structural & Base Steel & Footings | Floor Bearer (pair) — 4kPa Zone | Floor Bearer ¦ 4kPa Zone, pair | nr | 2 | inferred | project_config: ceil(span_short(7.2m) / bearer_spacing(1.8m) × fraction(0.3)) | project_config: main_floor_area=64.80m² × fraction(0.3) = 19.44m²; joist_spacing=450mm; bearer_spacing=1800mm; span=dxf_geometry: DXF: floor=86.4m² perim=38.4m → L=12.0m W=7.2m; verandah=21.6m² depth=3.0m (engineering inference: full-width attachment); main=64.8m² (9.0m×7.2m); span=7.2m run=9.0m | ceil(7.2/1.8 × 0.3) | LOW
G07 | 50107 | 50107 - Structural & Base Steel & Footings | Floor Sheet (FC / plywood) | FC Sheet Floor ¦ 18mm thk, 1200 x 2400 Sheet | sheets | 24 | calculated | ceil(floor_area × 1.05 / 2.88) | project_config+dxf_geometry: floor_area=64.80 m² | ceil(64.80 × 1.05 / 2.88) | LOW
G08 | 50107 | 50107 - Structural & Base Steel & Footings | Floor Sheet Fixing Screws | Fixing ¦ FC Floor Sheet Screw | boxes | 2 | calculated | ceil(sheet_count × 16 fixings / 200 per box) | project_config+dxf_geometry: sheet_count=24 | ceil(sheets × 16 / 200) | LOW
H01 | 50107 | 50107 - Structural & Base Steel & Footings | Strip Footing — External Perimeter | Substructure ¦ Strip Footing, External Perimeter | lm | 38.4 | calculated | #NAME? | derived_steel_floor: perimeter=38.4 m | #NAME? | MEDIUM
H02 | 50107 | 50107 - Structural & Base Steel & Footings | Strip Footing — Concrete Volume | Substructure ¦ Strip Footing Concrete Volume | m3 | 7.68 | calculated | perimeter × 0.5 m depth × 0.4 m width | derived_steel_floor: 38.4 × 0.5 × 0.4 | 38.4 × 0.5 × 0.4 | LOW
H03 | 50107 | 50107 - Structural & Base Steel & Footings | Strip Footing — Formwork | Substructure ¦ Strip Footing Formwork | lm | 38.4 | calculated | #NAME? | derived_steel_floor: perimeter=38.4 m | #NAME? | MEDIUM
H04 | 50107 | 50107 - Structural & Base Steel & Footings | Bulk Earthworks / Level (provisional) | Substructure ¦ Bulk Earthworks / Level (provisional) | m3 | 0 | placeholder | site survey required | no site survey in sources | manual review required | LOW
H05 | 50107 | 50107 - Structural & Base Steel & Footings | Strip Footing — Internal Bearing Lines | Substructure ¦ Strip Footing, Internal Bearing | lm | 29.4 | calculated | #NAME? | dxf_geometry: int_wall_lm=29.4 m | #NAME? | MEDIUM
H06 | 50107 | 50107 - Structural & Base Steel & Footings | Strip Footing Internal — Concrete Volume | Substructure ¦ Strip Footing, Internal Bearing | m3 | 5.88 | calculated | int_lm × 0.5 m depth × 0.4 m width | derived: 29.4 × 0.5 × 0.4 | 29.4 × 0.5 × 0.4 | LOW
H07 | 50107 | 50107 - Structural & Base Steel & Footings | Pad Footing (concrete) | Substructure ¦ Pad Footing, Concrete | nr | 15 | measured | dxf_geometry: pad_count | dxf_geometry: count=15 | direct count | MEDIUM
H08 | 50107 | 50107 - Structural & Base Steel & Footings | Pad Footing Concrete (m3) | Substructure ¦ Pad Footing Concrete Volume | m3 | 5.145 | calculated | count × 0.7×0.7×0.7 m = 0.343 m³ each | derived: 15 pads × 0.343 m³ | 15 × 0.343 | LOW
A12 | 50111 | 50111 - Fixings & Connectors | Framing Screw 12G-14×20 HEX Head (LGS stud-to-track) | Fixing ¦ 12G-14x20mm HEX Head, DP | boxes | 19 | calculated | wall_frame_lm(2300.4) × 4.0 screws/m ÷ 500/box | framecad_bom: wall=2300.4lm, roof_panel=481.7lm, batten=1385.3lm; dxf: pad_count=15, strip_perim=0.0m | ceil(2300.4 × 4.0 / 500) | MEDIUM
A13 | 50111 | 50111 - Fixings & Connectors | Framing Screw 10G-24×40 Countersunk (roof panel) | Fixing ¦ 10G-24x40mm Countersunk, DP | boxes | 3 | calculated | roof_panel_lm(481.7) × 3.0 screws/m ÷ 500/box | framecad_bom: wall=2300.4lm, roof_panel=481.7lm, batten=1385.3lm; dxf: pad_count=15, strip_perim=0.0m | ceil(481.7 × 3.0 / 500) | MEDIUM
A14 | 50111 | 50111 - Fixings & Connectors | Framing Screw 10G-14×16 Wafer Head (batten-to-purlin) | Fixing ¦ 10G-14x16mm Wafer Head, DP | boxes | 7 | calculated | batten_lm(1385.3) × 2.5 screws/m ÷ 500/box | framecad_bom: wall=2300.4lm, roof_panel=481.7lm, batten=1385.3lm; dxf: pad_count=15, strip_perim=0.0m | ceil(1385.3 × 2.5 / 500) | LOW
A15 | 50111 | 50111 - Fixings & Connectors | Sleeve Anchor M12×75 — Pad Footings | Fixing ¦ M12 x 75mm Sleeve Anchor (Pad Footings) | nr | 60 | calculated | pad_count(15) × 4 anchors per pad | dxf_geometry: pad_count=15 (DXF STRUCTURE layer) | 15 × 4 | MEDIUM
A16 | 50111 | 50111 - Fixings & Connectors | PH Post Holder Bracket (PHA/PHB/PHD) | PH Bracket ¦ Post Holder (PHA/PHB/PHD) | nr | 28 | calculated | steel_shs_lm(96.7) ÷ avg_height(3.5m) | ifc_model: steel_shs_lm=96.69 / avg_height(3.5m) | ceil(96.7/3.5) | LOW
A17 | 50111 | 50111 - Fixings & Connectors | Triple Grip Connector (roof-to-wall uplift) | Accessories ¦ Triple Grip Connector (Pryda) | nr | 36 | calculated | eaves_lm(42.4) ÷ spacing(1.2m) | dxf_geometry: eaves_length=42.4m | ceil(42.4 / 1.2) | LOW
A18 | 50111 | 50111 - Fixings & Connectors | Hold-Down Washer — Cyclonic (post base) | Accessories ¦ Hold Down Washer, Cyclonic | nr | 60 | calculated | pad_count(15) × 4 washers per pad | dxf_geometry: pad_count=15 | 15 × 4 | LOW
A19 | 50111 | 50111 - Fixings & Connectors | Fix Plate / Gusset Plate (strap bracing connection) | Accessories ¦ Fix Plate Connector, G350 | nr | 18 | calculated | wall_strap_lm(49.7) × 0.35 plates/m | framecad_bom: wall_strap_lm=49.73lm | ceil(49.7 × 0.35) | LOW
A20 | 50111 | 50111 - Fixings & Connectors | Diagonal Strap Tensioner / Anchor (bracing strap end) | Accessories ¦ Strap Brace Tensioner | nr | 34 | calculated | strap_runs(17) × 2 ends | framecad_bom: wall_strap_lm=49.73lm | ceil(49.7/3.0) × 2 | LOW
A21 | 50111 | 50111 - Fixings & Connectors | Cable Grommet (LGS service penetration) | Accessories ¦ Grommet 35mm Dia | nr | 45 | inferred | int_wall_lm(29.4) × 1.5 grommets/m | dxf_geometry: int_wall_lm=29.4m | ceil(29.4 × 1.5) | LOW
A22 | 50111 | 50111 - Fixings & Connectors | Structural Fixings Remainder — Hex Bolts / Angles / Misc (PLACEHOLDER) | Fixing ¦ Structural Fixings Remainder (PLACEHOLDER) | item | 0 | placeholder | no FrameCAD connection schedule — grouped items not derivable | no fixing schedule in source documents | manual review required | LOW
B01 | 50112 | 50112 - Roof & Roof Plumbing | Sisalation / Sarking | Insulation ¦ Sisalation / Sarking | rolls | 2 | calculated | ceil(roof_area / 73.0 m²/roll) | dxf_geometry: roof_area=106.60 m² | ceil(106.60 / 73.0) | HIGH
B02 | 50112 | 50112 - Roof & Roof Plumbing | Roof Tek Screws | Fixing ¦ Roof Tek Screw, Hex Head, DP | boxes | 11 | calculated | assembly_rule:roof_cladding | dxf_geometry: roof_area=106.60 m² | roof_cladding → ceil(x / 10) [note: 1 box per 10 m² (approx 250 screws/box at 25 screws/m²)] | MEDIUM
B03 | 50112 | 50112 - Roof & Roof Plumbing | Roof Cladding Sheet (corrugated / CGI) | Roof Cladding ¦ Custom Orb Corrugated CGI Sheet | sheets | 49 | calculated | area×waste / (cover_w×sheet_len) = 106.6×1.05/(0.762×3.0m) | dxf_geometry: roof_area=106.60 m², eaves_lm=42.40 m | ceil(area × 1.05 / (0.762 × 3.0m)) | MEDIUM
B04 | 50112 | 50112 - Roof & Roof Plumbing | Ridge Capping | Ridge Cap ¦ Galvanised, lm | lm | 10.6 | calculated | assembly_rule:roof_ridge | dxf_geometry: ridge_length=10.60 lm | roof_ridge → x | MEDIUM
B05 | 50112 | 50112 - Roof & Roof Plumbing | Ridge Cap Fixing Screws | Fixing ¦ Ridge Cap Hex Head Screw | nr | 36 | calculated | assembly_rule:roof_ridge | dxf_geometry: ridge_length=10.60 lm | roof_ridge → ceil(x / 0.3) [note: 1 screw per 300 mm] | MEDIUM
B06 | 50112 | 50112 - Roof & Roof Plumbing | Ridge End Cap | Ridge End Cap ¦ Galvanised | nr | 2 | calculated | assembly_rule:roof_ridge | dxf_geometry: ridge_length=10.60 lm | roof_ridge → 2 [note: 2 end caps per ridge run (one each end)] | MEDIUM
B07 | 50112 | 50112 - Roof & Roof Plumbing | Fascia Board | Fascia Board ¦ Galvanised, lm | lm | 42.4 | calculated | assembly_rule:roof_eaves | dxf_geometry: eaves_length=42.40 lm | roof_eaves → x | MEDIUM
B08 | 50112 | 50112 - Roof & Roof Plumbing | Fascia Clips | Fascia ¦ Clips | nr | 71 | calculated | assembly_rule:roof_eaves | dxf_geometry: eaves_length=42.40 lm | roof_eaves → ceil(x / 0.6) [note: 1 clip per 600 mm] | MEDIUM
B09 | 50112 | 50112 - Roof & Roof Plumbing | Birdproof Foam Strip | Accessories ¦ Birdproof Foam Strip | lm | 42.4 | calculated | assembly_rule:roof_eaves | dxf_geometry: eaves_length=42.40 lm | roof_eaves → x [note: runs full eaves length] | MEDIUM
B10 | 50112 | 50112 - Roof & Roof Plumbing | Eaves Gutter | SL-14 ¦ PVC Box Gutter | lm | 42.4 | calculated | assembly_rule:roof_eaves | dxf_geometry: eaves_length=42.40 lm | roof_eaves → x | MEDIUM
B11 | 50112 | 50112 - Roof & Roof Plumbing | Gutter Joiner | SL-14 ¦ PVC Gutter Joiner | nr | 3 | calculated | assembly_rule:roof_eaves | dxf_geometry: eaves_length=42.40 lm | roof_eaves → max(0, ceil(x / 6.0) - ceil(x / 10)) [note: PVC box gutter 6 m stock: joiners = total_lengths − estimated_run_count (≈eaves/10 m per run)] | MEDIUM
B12 | 50112 | 50112 - Roof & Roof Plumbing | Gutter Stop End | SL-14 ¦ PVC Gutter Stop End | nr | 6 | calculated | assembly_rule:roof_eaves | dxf_geometry: eaves_length=42.40 lm | roof_eaves → max(2, ceil(x / 20) * 2) [note: 2 per run; add 2 per extra run > 20 m] | MEDIUM
B13 | 50112 | 50112 - Roof & Roof Plumbing | Barge Capping | Barge Cap ¦ Galvanised, lm | lm | 8.5 | calculated | assembly_rule:roof_barge | dxf_geometry: barge_length=8.50 lm | roof_barge → x | LOW
B14 | 50112 | 50112 - Roof & Roof Plumbing | Barge End Cap | Barge End Cap ¦ Galvanised | nr | 2 | calculated | assembly_rule:roof_barge | dxf_geometry: barge_length=8.50 lm | roof_barge → 2 [note: 2 end caps per barge run (ridge peak and eaves)] | LOW
B15 | 50112 | 50112 - Roof & Roof Plumbing | PVC Downpipe | SL-14 ¦ PVC Downpipe, 68mm | nr | 6 | calculated | assembly_rule:roof_drainage | dxf_geometry: downpipe_count=6 | roof_drainage → x | MEDIUM
B16 | 50112 | 50112 - Roof & Roof Plumbing | Gutter Drop Outlet | SL-14 ¦ PVC Gutter Drop Outlet | nr | 6 | calculated | assembly_rule:roof_drainage | dxf_geometry: downpipe_count=6 | roof_drainage → x | MEDIUM
B17 | 50112 | 50112 - Roof & Roof Plumbing | Downpipe Elbow (90°) | SL-14 ¦ PVC Downpipe Elbow, 90° | nr | 12 | calculated | assembly_rule:roof_drainage | dxf_geometry: downpipe_count=6 | roof_drainage → x * 2 [note: top + bottom elbow per downpipe] | MEDIUM
B18 | 50112 | 50112 - Roof & Roof Plumbing | Downpipe Clip / Saddle | SL-14 ¦ PVC Downpipe Clip | nr | 18 | calculated | assembly_rule:roof_drainage | dxf_geometry: downpipe_count=6 | roof_drainage → x * 3 [note: approx 3 clips per 3 m drop] | MEDIUM
K04 | 50113 | 50113 - External Cladding | External Wall Cladding — FC Weatherboard (supply & fix) | External Cladding ¦ FC Weatherboard | m2 | 87.14 | calculated | ext_wall_lm(38.40) × wall_h(2.4) − opening_area | dxf_geometry: ext_wall_perimeter=38.40 m, h=2.4 m | 38.40 × 2.4 − 5.02 | HIGH
K05 | 50113 | 50113 - External Cladding | FC Weatherboard — Board Count | External Cladding ¦ FC Weatherboard | nr | 126 | calculated | rows_of_boards=12 (h=2400mm / 200mm exp) × boards_per_row=10 (lm=38.4m / 4.2m) × waste=1.05 | dxf_geometry: ext_lm=38.40 m, wall_h=2.4 m | ceil(h/exp) × ceil(lm/board_l) × waste | MEDIUM
K06 | 50113 | 50113 - External Cladding | FC Weatherboard H-Joiner Extrusion | External Cladding ¦ FC Weatherboard | nr | 72 | calculated | per-façade: 2×L-face (2×2=4 joiners/row) + 2×W-face (1×2=2 joiners/row) × 12 rows; derived from floor L=12.0m W=7.2m | dxf_geometry: floor_area=86.4m² + ext_perim=38.4m → L=12.0m W=7.2m | per-façade: joiners per face × rows_of_boards | MEDIUM
K07 | 50113 | 50113 - External Cladding | External Corner Flashing (FC cladding) | External Cladding ¦ Corner Flashing, Galvanised | nr | 4 | inferred | rectangular footprint: L=12.0m × W=7.2m (2×(L+W)=38.4m ≈ measured perim 38.4m) | dxf_geometry: ext_wall_perimeter=38.4m, floor_area=86.4m² → L=12.0m W=7.2m | geometry-derived corner count | MEDIUM
K08 | 50113 | 50113 - External Cladding | External Corner Trim / Angle Bead | External Cladding ¦ Corner Trim / Angle Bead | lm | 9.6 | calculated | ext_corners(4) × wall_h(2.4m) | derived: 4 corners × 2.4 m | corners × wall_height | MEDIUM
K09 | 50113 | 50113 - External Cladding | FC Weatherboard Stud Fixing Clip | External Cladding ¦ FC Weatherboard | nr | 768 | calculated | studs(64) × rows_of_boards(12) [stud_spacing=600mm] | dxf_geometry: ext_lm=38.40 m, stud_spacing=600mm | ceil(ext_lm × studs_per_m) × rows_of_boards | MEDIUM
K10 | 50113 | 50113 - External Cladding | Stainless Steel Screw — Cladding Fix | Fixing ¦ Stainless Steel Screw (Cladding) | nr | 1536 | calculated | stud_clips(768) × 2 screws per clip | derived from clip count: 768 | clip_count × 2 | LOW
K11 | 50113 | 50113 - External Cladding | Building Wrap / Sarking — External Wall | Accessories ¦ Building Wrap / Sarking | m2 | 96.77 | calculated | gross_wall_area(92.16) × 1.05 overlap | dxf_geometry: ext_lm=38.40 m × wall_h=2.4 m | ext_lm × wall_h × 1.05 | MEDIUM
K12 | 50113 | 50113 - External Cladding | Verandah Decking / Slab | External Works ¦ Verandah Decking | m2 | 21.6 | measured | DXF VERANDAH LWPOLYLINE area | dxf_geometry: verandah_area=21.60 m² | #NAME? | HIGH
K13 | 50113 | 50113 - External Cladding | Site Preparation (Provisional) | Substructure ¦ Site Preparation (Provisional) | item | 0 | placeholder | provisional allowance — no site survey | no site survey in sources | manual review required | LOW
D01 | 50114 | 50114 - Openings | Door — DOOR_90 (920mm) | Door ¦ 920mm Wide (DOOR_90) | nr | 1 | measured | count from source | dxf_blocks: mark=DOOR_90 count=1 | direct count | HIGH
D02 | 50114 | 50114 - Openings | Door — DOOR_82 (820mm) | Door ¦ 820mm Wide (DOOR_82) | nr | 4 | measured | count from source | dxf_blocks: mark=DOOR_82 count=4 | direct count | HIGH
D03 | 50114 | 50114 - Openings | Door — DOOR_72 (720mm) | Door ¦ 720mm Wide (DOOR_72) | nr | 1 | measured | count from source | dxf_blocks: mark=DOOR_72 count=1 | direct count | HIGH
D04 | 50114 | 50114 - Openings | Door Head Flashing | Flashing ¦ Door Head, Galvanised | lm | 5.52 | calculated | sum((door_width + 50mm overrun × 2) × count) | dxf_blocks: door widths DOOR_90=0.92m×1, DOOR_82=0.82m×4, DOOR_72=0.72m×1 | sum((width + 0.100) × qty) | MEDIUM
D05 | 50114 | 50114 - Openings | Door Sill Flashing | Flashing ¦ Door Sill, Galvanised | lm | 5.52 | calculated | sum((door_width + 50mm overrun × 2) × count) | dxf_blocks: 6 doors | sum((width + 0.100) × qty) | MEDIUM
D06 | 50114 | 50114 - Openings | Door Leaf | Door ¦ Leaf | nr | 1 | calculated | assembly_rule:door_single_hinged | dxf_blocks: DOOR_90 count=1 | door_single_hinged → x | HIGH
D07 | 50114 | 50114 - Openings | Door Frame Set | Door ¦ Frame Set | nr | 1 | calculated | assembly_rule:door_single_hinged | dxf_blocks: DOOR_90 count=1 | door_single_hinged → x | HIGH
D08 | 50114 | 50114 - Openings | Door Hinge (pair) | Door ¦ Hinge (pair) | nr | 3 | calculated | assembly_rule:door_single_hinged | dxf_blocks: DOOR_90 count=1 | door_single_hinged → x * 3 [note: 3 pairs per door (standard)] | MEDIUM
D09 | 50114 | 50114 - Openings | Door Lockset | Door ¦ Lockset | nr | 1 | calculated | assembly_rule:door_single_hinged | dxf_blocks: DOOR_90 count=1 | door_single_hinged → x | HIGH
D10 | 50114 | 50114 - Openings | Door Stop | Door ¦ Stop | nr | 1 | calculated | assembly_rule:door_single_hinged | dxf_blocks: DOOR_90 count=1 | door_single_hinged → x | HIGH
D11 | 50114 | 50114 - Openings | Door Leaf | Door ¦ Leaf | nr | 4 | calculated | assembly_rule:door_single_hinged | dxf_blocks: DOOR_82 count=4 | door_single_hinged → x | HIGH
D12 | 50114 | 50114 - Openings | Door Frame Set | Door ¦ Frame Set | nr | 4 | calculated | assembly_rule:door_single_hinged | dxf_blocks: DOOR_82 count=4 | door_single_hinged → x | HIGH
D13 | 50114 | 50114 - Openings | Door Hinge (pair) | Door ¦ Hinge (pair) | nr | 12 | calculated | assembly_rule:door_single_hinged | dxf_blocks: DOOR_82 count=4 | door_single_hinged → x * 3 [note: 3 pairs per door (standard)] | MEDIUM
D14 | 50114 | 50114 - Openings | Door Lockset | Door ¦ Lockset | nr | 4 | calculated | assembly_rule:door_single_hinged | dxf_blocks: DOOR_82 count=4 | door_single_hinged → x | HIGH
D15 | 50114 | 50114 - Openings | Door Stop | Door ¦ Stop | nr | 4 | calculated | assembly_rule:door_single_hinged | dxf_blocks: DOOR_82 count=4 | door_single_hinged → x | HIGH
D16 | 50114 | 50114 - Openings | Door Leaf | Door ¦ Leaf | nr | 1 | calculated | assembly_rule:door_single_hinged | dxf_blocks: DOOR_72 count=1 | door_single_hinged → x | HIGH
D17 | 50114 | 50114 - Openings | Door Frame Set | Door ¦ Frame Set | nr | 1 | calculated | assembly_rule:door_single_hinged | dxf_blocks: DOOR_72 count=1 | door_single_hinged → x | HIGH
D18 | 50114 | 50114 - Openings | Door Hinge (pair) | Door ¦ Hinge (pair) | nr | 3 | calculated | assembly_rule:door_single_hinged | dxf_blocks: DOOR_72 count=1 | door_single_hinged → x * 3 [note: 3 pairs per door (standard)] | MEDIUM
D19 | 50114 | 50114 - Openings | Door Lockset | Door ¦ Lockset | nr | 1 | calculated | assembly_rule:door_single_hinged | dxf_blocks: DOOR_72 count=1 | door_single_hinged → x | HIGH
D20 | 50114 | 50114 - Openings | Door Stop | Door ¦ Stop | nr | 1 | calculated | assembly_rule:door_single_hinged | dxf_blocks: DOOR_72 count=1 | door_single_hinged → x | HIGH
D21 | 50114 | 50114 - Openings | Window — WINDOW_LOUVRE_1100 | Window ¦ Louvre, 1100mm Wide | nr | 8 | measured | count from source | dxf_blocks: mark=WINDOW_LOUVRE_1100 count=8 | direct count | MEDIUM
D22 | 50114 | 50114 - Openings | Window — WINDOW_LOUVRE_800 | Window ¦ Louvre, 800mm Wide | nr | 2 | measured | count from source | dxf_blocks: mark=WINDOW_LOUVRE_800 count=2 | direct count | MEDIUM
D23 | 50114 | 50114 - Openings | Window — WINDOW_LOUVRE_1800 | Window ¦ Louvre, 1800mm Wide | nr | 1 | measured | count from source | dxf_blocks: mark=WINDOW_LOUVRE_1800 count=1 | direct count | MEDIUM
D24 | 50114 | 50114 - Openings | Window Head Flashing — WINDOW_LOUVRE_1100 | Flashing ¦ Window Head, Galvanised | lm | 9.44 | calculated | (window_width + 50mm overrun × 2) × count = (1.08+0.100)×8 | dxf_blocks: block_name: WINDOW_LOUVRE_1100 count=8 | (1.08+0.100)×8 | MEDIUM
D25 | 50114 | 50114 - Openings | Window Sill Flashing — WINDOW_LOUVRE_1100 | Flashing ¦ Window Sill, Galvanised | lm | 9.44 | calculated | (window_width + 50mm overrun × 2) × count = (1.08+0.100)×8 | dxf_blocks: block_name: WINDOW_LOUVRE_1100 count=8 | (1.08+0.100)×8 | MEDIUM
D26 | 50114 | 50114 - Openings | Louvre Blade — WINDOW_LOUVRE_1100 | Window ¦ Louvre Blade, 1100mm Wide | nr | 64 | calculated | ceil(frame_h(750mm) / 100mm pitch) × count = 8 blades × 8 | dxf_blocks: config_default=750mm count=8 | ceil(750/100) × 8 | LOW
D27 | 50114 | 50114 - Openings | Window Head Flashing — WINDOW_LOUVRE_800 | Flashing ¦ Window Head, Galvanised | lm | 1.8 | calculated | (window_width + 50mm overrun × 2) × count = (0.80+0.100)×2 | dxf_blocks: block_name: WINDOW_LOUVRE_800 count=2 | (0.80+0.100)×2 | MEDIUM
D28 | 50114 | 50114 - Openings | Window Sill Flashing — WINDOW_LOUVRE_800 | Flashing ¦ Window Sill, Galvanised | lm | 1.8 | calculated | (window_width + 50mm overrun × 2) × count = (0.80+0.100)×2 | dxf_blocks: block_name: WINDOW_LOUVRE_800 count=2 | (0.80+0.100)×2 | MEDIUM
D29 | 50114 | 50114 - Openings | Louvre Blade — WINDOW_LOUVRE_800 | Window ¦ Louvre Blade, 800mm Wide | nr | 16 | calculated | ceil(frame_h(750mm) / 100mm pitch) × count = 8 blades × 2 | dxf_blocks: config_default=750mm count=2 | ceil(750/100) × 2 | LOW
D30 | 50114 | 50114 - Openings | Window Head Flashing — WINDOW_LOUVRE_1800 | Flashing ¦ Window Head, Galvanised | lm | 1.95 | calculated | (window_width + 50mm overrun × 2) × count = (1.85+0.100)×1 | dxf_blocks: block_name: WINDOW_LOUVRE_1800 count=1 | (1.85+0.100)×1 | MEDIUM
D31 | 50114 | 50114 - Openings | Window Sill Flashing — WINDOW_LOUVRE_1800 | Flashing ¦ Window Sill, Galvanised | lm | 1.95 | calculated | (window_width + 50mm overrun × 2) × count = (1.85+0.100)×1 | dxf_blocks: block_name: WINDOW_LOUVRE_1800 count=1 | (1.85+0.100)×1 | MEDIUM
D32 | 50114 | 50114 - Openings | Louvre Blade — WINDOW_LOUVRE_1800 | Window ¦ Louvre Blade, 1800mm Wide | nr | 8 | calculated | ceil(frame_h(750mm) / 100mm pitch) × count = 8 blades × 1 | dxf_blocks: config_default=750mm count=1 | ceil(750/100) × 1 | LOW
D33 | 50114 | 50114 - Openings | Louvre Window Frame | Window ¦ Louvre Frame | nr | 8 | calculated | assembly_rule:window_louvre | dxf_blocks: WINDOW_LOUVRE_1100 count=8 | window_louvre → x | MEDIUM
D34 | 50114 | 50114 - Openings | Louvre Blade Set | Window ¦ Louvre Blade | nr | 8 | calculated | assembly_rule:window_louvre | dxf_blocks: WINDOW_LOUVRE_1100 count=8 | window_louvre → x | MEDIUM
D35 | 50114 | 50114 - Openings | Flyscreen | Window ¦ Fly Screen | nr | 8 | calculated | assembly_rule:window_louvre | dxf_blocks: WINDOW_LOUVRE_1100 count=8 | window_louvre → x | MEDIUM
D36 | 50114 | 50114 - Openings | Louvre Window Frame | Window ¦ Louvre Frame | nr | 2 | calculated | assembly_rule:window_louvre | dxf_blocks: WINDOW_LOUVRE_800 count=2 | window_louvre → x | MEDIUM
D37 | 50114 | 50114 - Openings | Louvre Blade Set | Window ¦ Louvre Blade | nr | 2 | calculated | assembly_rule:window_louvre | dxf_blocks: WINDOW_LOUVRE_800 count=2 | window_louvre → x | MEDIUM
D38 | 50114 | 50114 - Openings | Flyscreen | Window ¦ Fly Screen | nr | 2 | calculated | assembly_rule:window_louvre | dxf_blocks: WINDOW_LOUVRE_800 count=2 | window_louvre → x | MEDIUM
D39 | 50114 | 50114 - Openings | Louvre Window Frame | Window ¦ Louvre Frame | nr | 1 | calculated | assembly_rule:window_louvre | dxf_blocks: WINDOW_LOUVRE_1800 count=1 | window_louvre → x | MEDIUM
D40 | 50114 | 50114 - Openings | Louvre Blade Set | Window ¦ Louvre Blade | nr | 1 | calculated | assembly_rule:window_louvre | dxf_blocks: WINDOW_LOUVRE_1800 count=1 | window_louvre → x | MEDIUM
D41 | 50114 | 50114 - Openings | Flyscreen | Window ¦ Fly Screen | nr | 1 | calculated | assembly_rule:window_louvre | dxf_blocks: WINDOW_LOUVRE_1800 count=1 | window_louvre → x | MEDIUM
D42 | 50114 | 50114 - Openings | Fly Screen — WINDOW_LOUVRE_1100 | Window ¦ Fly Screen, 1100mm Wide | m2 | 6.48 | calculated | width(1.08m) × height(0.750m) × qty(8) | dxf_blocks: mark=WINDOW_LOUVRE_1100 w=1.08m (block_name) h=0.750m (config_default=750mm) qty=8 | 1.08 × 0.750 × 8 | LOW
D43 | 50114 | 50114 - Openings | Fly Screen — WINDOW_LOUVRE_800 | Window ¦ Fly Screen, 800mm Wide | m2 | 1.2 | calculated | width(0.80m) × height(0.750m) × qty(2) | dxf_blocks: mark=WINDOW_LOUVRE_800 w=0.80m (block_name) h=0.750m (config_default=750mm) qty=2 | 0.80 × 0.750 × 2 | LOW
D44 | 50114 | 50114 - Openings | Fly Screen — WINDOW_LOUVRE_1800 | Window ¦ Fly Screen, 1800mm Wide | m2 | 1.39 | calculated | width(1.85m) × height(0.750m) × qty(1) | dxf_blocks: mark=WINDOW_LOUVRE_1800 w=1.85m (block_name) h=0.750m (config_default=750mm) qty=1 | 1.85 × 0.750 × 1 | LOW
D45 | 50114 | 50114 - Openings | Door Closer — Hydraulic (main entrance) | Door ¦ Closer, Hydraulic | nr | 1 | inferred | entrance_door_count(1) — widest door mark(s) in pharmacy | dxf_blocks: DOOR_90 (width≥850mm or DOOR_90) | count of entrance-width doors | MEDIUM
F02 | 50114 | 50114 - Openings | Architrave — Door | Timber Architrave ¦ 12 x 75 x 2400mm Timber | lm | 36 | calculated | door_count × 6.0 lm/door = 6 × 6.0 | derived from door_count=6 | door_count × 6.0 | MEDIUM
F03 | 50114 | 50114 - Openings | Architrave — Window | Timber Architrave ¦ 12 x 75 x 2400mm Timber | lm | 52.8 | calculated | window_count × 4.8 lm/window = 11 × 4.8 | derived from window_count=11 | window_count × 4.8 | MEDIUM
E01 | 50115 | 50115 - Internal Linings & Ceilings | External Wall Lining — FC Sheet (6mm, 1200×2700) | External Lining ¦ FC Sheet, 1200 x 2400mm | sheets | 27 | calculated | ceil(ext_wall_area_net × 1.05 / 3.24) | dxf_geometry: ext_wall_lm=38.40 m × h=2.4 m → gross=92.16 m² − openings=10.941 m² → net=81.22 m² | ceil(81.22 × 1.05 / 3.24) | MEDIUM
E02 | 50115 | 50115 - Internal Linings & Ceilings | External Wall Lining — FC Sheet Screws | Fixing ¦ FC Sheet Screw (External) | boxes | 11 | calculated | ceil(wall_area_net × 25 screws/m² / 200/box) | derived from ext_wall_area_net=81.22 m² | ceil(area × 25 / 200) | LOW
E03 | 50115 | 50115 - Internal Linings & Ceilings | Internal Wall Lining — FC Sheet (6mm, 1200×2700) | Internal Lining ¦ FC Sheet, 1200 x 2400mm | sheets | 41 | calculated | ceil(int_wall_area_net × 1.05 / 3.24) | dxf_geometry: int_wall_lm=29.40 m × h=2.4 m × 2 faces = 141.12 m² − int_doors=16.320 m² → net=124.80 m² | ceil(124.80 × 1.05 / 3.24) | HIGH
E04 | 50115 | 50115 - Internal Linings & Ceilings | Internal Wall Lining — FC Sheet Screws | Fixing ¦ FC Sheet Screw (Internal) | boxes | 16 | calculated | ceil(both_face_area_net × 25 screws/m² / 200/box) | derived from int_wall_area_both_net=124.80 m² | ceil(area × 25 / 200) | LOW
E05 | 50115 | 50115 - Internal Linings & Ceilings | Internal Wall Lining — FC Sheet Joiner Strip | Internal Lining Accessory ¦ PVC H Joiner | lm | 117.6 | calculated | ceil(face_lm / 1.2) × h = ceil(58.8/1.2) × 2.4 | dxf_geometry: int_wall_lm=29.40 m × 2 faces = 58.8 lm | ceil(58.8/1.2) × 2.4 | LOW
E06 | 50115 | 50115 - Internal Linings & Ceilings | Wet Area Wall Lining — Waterproof Board / FC | Internal Lining ¦ Waterproof Board / FC, Wet Area | sheets | 7 | inferred | ceil(wet_room_wall_area × 1.05 / 3.24) | rooms=['Toilet']: total_wet_wall_area≈20.40 m² | sum(4×sqrt(room_area)×h) → ceil(×1.05/3.24) | LOW
E07 | 50115 | 50115 - Internal Linings & Ceilings | Ceiling Lining — FC Sheet (6mm, 1200×2400) | Ceiling Lining ¦ FC Sheet, 1200 x 2400mm | sheets | 24 | calculated | ceil(ceiling_area × 1.05 / 2.88) | derived: ceiling_area=64.80 m² | ceil(64.80 × 1.05 / 2.88) | MEDIUM
E08 | 50115 | 50115 - Internal Linings & Ceilings | Ceiling Batten (LGS / timber) | Ceiling Batten ¦ G22 | lm | 162 | calculated | ceiling_area / (400 mm spacing) | derived: ceiling_area=64.80 m² | 64.80 / 0.4 | MEDIUM
E09 | 50115 | 50115 - Internal Linings & Ceilings | Ceiling FC Sheet Screws | Fixing ¦ FC Sheet Screw (Ceiling) | boxes | 7 | calculated | ceil(ceil_area × 20 screws/m² / 200/box) | derived from ceiling_area=64.80 m² | ceil(area × 20 / 200) | LOW
E10 | 50115 | 50115 - Internal Linings & Ceilings | Verandah Soffit Lining — FC Sheet (6mm, 1200×2400) | Verandah Soffit Lining — FC Sheet (6mm, 1200×2400) | sheets | 8 | calculated | ceil(verandah_soffit_area × 1.05 / 2.88) | dxf_geometry: verandah_area=21.60 m² (soffit = verandah deck area) | ceil(21.60 × 1.05 / 2.88) | HIGH
E11 | 50115 | 50115 - Internal Linings & Ceilings | Verandah Soffit Batten (LGS / timber) | Verandah Soffit Batten (LGS / timber) | lm | 54 | calculated | verandah_soffit_area / (400 mm spacing) | dxf_geometry: verandah_soffit_area=21.60 m² | 21.60 / 0.4 | MEDIUM
E12 | 50115 | 50115 - Internal Linings & Ceilings | Cornice / Ceiling Trim | Timber Cornice ¦ 25 x 25 x 2400mm Timber | lm | 38.4 | calculated | #NAME? | dxf_geometry: ext_wall_perimeter=38.40 m | cornice = ext_wall_perimeter | MEDIUM
I01 | 50117 | 50117 - Services (Hydraulics — Partial) | Hand Basin (dispensary) | Hydraulics ¦ Hand Basin | nr | 1 | inferred | room_template:pharmacy | room_schedule: Dispensary (type=pharmacy) | room_template:pharmacy → Hand Basin (dispensary) | LOW
I02 | 50117 | 50117 - Services (Hydraulics — Partial) | Tapware (basin) | Hydraulics ¦ Tapware | set | 1 | inferred | room_template:pharmacy | room_schedule: Dispensary (type=pharmacy) | room_template:pharmacy → Tapware (basin) | LOW
I03 | 50117 | 50117 - Services (Hydraulics — Partial) | Cold Room / Refrigeration Allowance | Services ¦ Cold Room / Refrigeration (PLACEHOLDER) | item | 1 | inferred | room_template:pharmacy | room_schedule: Dispensary (type=pharmacy) | room_template:pharmacy → Cold Room / Refrigeration Allowance | LOW
I04 | 50117 | 50117 - Services (Hydraulics — Partial) | Builder's Works — Electrical (pharmacy) | Services ¦ Builder's Works, Electrical | item | 1 | inferred | room_template:pharmacy | room_schedule: Dispensary (type=pharmacy) | room_template:pharmacy → Builder's Works — Electrical (pharmacy) | LOW
I05 | 50117 | 50117 - Services (Hydraulics — Partial) | Builder's Works — Services (unclassified room) | Services ¦ Builder's Works, Services | item | 1 | inferred | room_template:waiting | room_schedule: Waiting / Reception (type=waiting) | room_template:waiting → Builder's Works — Services (unclassified room) | LOW
I06 | 50117 | 50117 - Services (Hydraulics — Partial) | Hand Basin (consulting room) | Hydraulics ¦ Hand Basin | nr | 1 | inferred | room_template:consulting | room_schedule: Consultation Room (type=consulting) | room_template:consulting → Hand Basin (consulting room) | LOW
I07 | 50117 | 50117 - Services (Hydraulics — Partial) | Tapware (basin) | Hydraulics ¦ Tapware | set | 1 | inferred | room_template:consulting | room_schedule: Consultation Room (type=consulting) | room_template:consulting → Tapware (basin) | LOW
I08 | 50117 | 50117 - Services (Hydraulics — Partial) | Builder's Works — Plumbing (consulting) | Hydraulics ¦ Builder's Works (Plumbing) | item | 1 | inferred | room_template:consulting | room_schedule: Consultation Room (type=consulting) | room_template:consulting → Builder's Works — Plumbing (consulting) | LOW
I09 | 50117 | 50117 - Services (Hydraulics — Partial) | Builder's Works — Electrical (office) | Services ¦ Builder's Works, Electrical | item | 1 | inferred | room_template:office | room_schedule: Staff Room (type=office) | room_template:office → Builder's Works — Electrical (office) | LOW
I10 | 50117 | 50117 - Services (Hydraulics — Partial) | WC Pan (close-coupled) | Hydraulics ¦ WC Pan (close-coupled) | nr | 1 | inferred | room_template:toilet | room_schedule: Toilet (type=toilet) | room_template:toilet → WC Pan (close-coupled) | MEDIUM
I11 | 50117 | 50117 - Services (Hydraulics — Partial) | WC Cistern | Hydraulics ¦ WC Cistern | nr | 1 | inferred | room_template:toilet | room_schedule: Toilet (type=toilet) | room_template:toilet → WC Cistern | MEDIUM
I12 | 50117 | 50117 - Services (Hydraulics — Partial) | Hand Basin | Hydraulics ¦ Hand Basin | nr | 1 | inferred | room_template:toilet | room_schedule: Toilet (type=toilet) | room_template:toilet → Hand Basin | MEDIUM
I13 | 50117 | 50117 - Services (Hydraulics — Partial) | Tapware (basin) | Hydraulics ¦ Tapware | set | 1 | inferred | room_template:toilet | room_schedule: Toilet (type=toilet) | room_template:toilet → Tapware (basin) | MEDIUM
I14 | 50117 | 50117 - Services (Hydraulics — Partial) | Mirror / Medicine Cabinet | FFE ¦ Mirror | nr | 1 | inferred | room_template:toilet | room_schedule: Toilet (type=toilet) | room_template:toilet → Mirror / Medicine Cabinet | LOW
I15 | 50117 | 50117 - Services (Hydraulics — Partial) | Toilet Roll Holder | FFE ¦ Toilet Roll Holder | nr | 1 | inferred | room_template:toilet | room_schedule: Toilet (type=toilet) | room_template:toilet → Toilet Roll Holder | LOW
I16 | 50117 | 50117 - Services (Hydraulics — Partial) | Hand Towel Rail / Dryer | FFE ¦ Towel Rail | nr | 1 | inferred | room_template:toilet | room_schedule: Toilet (type=toilet) | room_template:toilet → Hand Towel Rail / Dryer | LOW
I17 | 50117 | 50117 - Services (Hydraulics — Partial) | Floor Waste | Hydraulics ¦ Floor Waste | nr | 1 | inferred | room_template:toilet | room_schedule: Toilet (type=toilet) | room_template:toilet → Floor Waste | MEDIUM
I18 | 50117 | 50117 - Services (Hydraulics — Partial) | Builder's Works — Plumbing (toilet) | Hydraulics ¦ Builder's Works (Plumbing) | item | 1 | inferred | room_template:toilet | room_schedule: Toilet (type=toilet) | room_template:toilet → Builder's Works — Plumbing (toilet) | MEDIUM
I19 | 50117 | 50117 - Services (Hydraulics — Partial) | Wet Area Wall Tiling — Toilet | Hydraulics ¦ WC Pan | m2 | 15.3 | inferred | perim_est(8.5m) × tile_height(1.8m) | room: Toilet (area=4.50 m², wet_area=True) | perim × 1.8m splash zone | LOW
I20 | 50117 | 50117 - Services (Hydraulics — Partial) | Wet Area Waterproofing — Membrane | Hydraulics ¦ Wet Area Waterproofing Membrane | m2 | 5.78 | inferred | room_area(4.50) + perim(8.5)×upstand(0.15m) | room: Toilet (area=4.50 m²) | room_area(4.50) + perim(8.5)×upstand(0.15m) | MEDIUM
I21 | 50117 | 50117 - Services (Hydraulics — Partial) | Builder's Works — Services (unclassified room) | Services ¦ Builder's Works, Services | item | 1 | inferred | room_template:store | room_schedule: Storage (type=store) | room_template:store → Builder's Works — Services (unclassified room) | LOW
I22 | 50117 | 50117 - Services (Hydraulics — Partial) | Air Conditioning / Mechanical Ventilation — PLACEHOLDER | Services ¦ Air Conditioning / Mechanical (PLACEHOLDER) | item | 0 | placeholder | no mechanical schedule in source documents | building_type=pharmacy: commercial building requires mechanical services | manual review required | LOW
I23 | 50117 | 50117 - Services (Hydraulics — Partial) | Exhaust Fan — Wet Area (toilet / laundry) | Electrical ¦ Exhaust Fan | item | 0 | placeholder | no mechanical schedule — wet area rooms require exhaust ventilation | building_type=pharmacy: wet area ventilation required by BCA F4.6 | manual review required | LOW
I24 | 50117 | 50117 - Services (Hydraulics — Partial) | Main Electrical Switchboard / Distribution Board | Electrical ¦ Main Switchboard / Distribution Board | item | 1 | inferred | whole_building_services template | floor_area=86.40 m² (building-wide) |  | LOW
I25 | 50117 | 50117 - Services (Hydraulics — Partial) | Main Water Meter / Stopcock | Hydraulics ¦ Main Water Meter / Stopcock | item | 1 | inferred | whole_building_services template | floor_area=86.40 m² (building-wide) |  | LOW
I26 | 50117 | 50117 - Services (Hydraulics — Partial) | Hot Water System (central) | Hydraulics ¦ Hot Water System | item | 1 | inferred | whole_building_services template | floor_area=86.40 m² (building-wide) |  | LOW
I27 | 50117 | 50117 - Services (Hydraulics — Partial) | Smoke Detectors (provisional) | Electrical ¦ Smoke Detector | nr | 3 | inferred | whole_building_services template | floor_area=86.40 m² (building-wide) | ceil(floor_area / 40) | LOW
C01 | 50118 | 50118 - Insulation | Insulation Batts — Roof / Ceiling | Insulation ¦ Glasswool Batts, Roof / Ceiling | m2 | 106.6 | calculated | #NAME? | dxf_geometry: roof_area=106.60 m² | #NAME? | HIGH
C02 | 50118 | 50118 - Insulation | Insulation Batts — External Wall | Insulation ¦ Glasswool Batts, External Wall | m2 | 92.16 | calculated | ext_wall_perimeter × wall_height | dxf_geometry: ext_wall_lm=38.40 × h=2.4 | 38.40 × 2.4 | MEDIUM
J01 | 50124 | 50124 - Stairs & Balustrades | Stair Stringer (Prefabricated Set) — 3 RISER | Stair ¦ Stringer | nr | 1 | inferred | project_config: stair evidence | project_config: STR-1 | DXF stair layer | LOW
J02 | 50124 | 50124 - Stairs & Balustrades | Stair Tread | Stair ¦ Tread | nr | 3 | inferred | flights × risers_per_flight = 1 × 3 | project_config: risers_per_flight=3 | 1 × 3 | LOW
J03 | 50124 | 50124 - Stairs & Balustrades | Stair Newel Post | Stair ¦ Component | nr | 2 | calculated | flights × 2 newel posts = 1 × 2 | project_config: STR-1 | 1 × 2 | MEDIUM
J04 | 50124 | 50124 - Stairs & Balustrades | Stair Balustrade — Top Rail | Balustrade ¦ Assembly | lm | 0.75 | calculated | #NAME? | project_config: STR-1 | run_est=0.75 m | LOW
J05 | 50124 | 50124 - Stairs & Balustrades | Stair Balustrade Post | Balustrade ¦ Post | nr | 1 | calculated | ceil(balustrade_lm / 1.2 m) = ceil(0.75/1.2) | project_config: balustrade_lm=0.75 m | ceil(lm / 1.2) | LOW
J06 | 50124 | 50124 - Stairs & Balustrades | Stair Balustrade Infill (glass / mesh / picket) | Balustrade ¦ Assembly | m2 | 0.75 | inferred | balustrade_lm × 1.0 m height = 0.75 × 1.0 | project_config: balustrade_lm=0.75 m | lm × 1.0 m infill height | LOW
J07 | 50124 | 50124 - Stairs & Balustrades | Stair Handrail | Balustrade ¦ Handrail | lm | 0.75 | calculated | #NAME? | project_config: STR-1 | run_est=0.75 m | LOW
J08 | 50124 | 50124 - Stairs & Balustrades | Access Ramp — Surface (concrete / non-slip) | Access Ramp ¦ Surface, Concrete / Non-slip | m2 | 8.82 | inferred | 1:14 gradient × 525mm entry height × 1.2m wide [stair: 3 risers × 175 mm = 525 mm] | derived from project_config: stair: 3 risers × 175 mm = 525 mm | 7.35 m run × 1.2 m wide | LOW
J09 | 50124 | 50124 - Stairs & Balustrades | Access Ramp — Handrail (both sides) | Access Ramp ¦ (type by design) | lm | 14.7 | inferred | ramp_run × 2 sides = 7.35 × 2 | derived from ramp run: 7.35 m (stair: 3 risers × 175 mm = 525 mm) | 7.35 × 2 | LOW
J10 | 50124 | 50124 - Stairs & Balustrades | Access Ramp — Edge Kerb / Guard | Access Ramp ¦ Edge Kerb / Guard | lm | 14.7 | inferred | ramp_run × 2 sides = 7.35 × 2 | derived from ramp run: 7.35 m (stair: 3 risers × 175 mm = 525 mm) | 7.35 × 2 | LOW
K01 | 50124 | 50124 - Stairs & Balustrades | Verandah Balustrade | Balustrade ¦ Assembly | lm | 20.4 | measured | DXF VERANDAH perimeter | dxf_geometry: verandah_perimeter=20.40 m | #NAME? | HIGH
K02 | 50124 | 50124 - Stairs & Balustrades | Verandah Handrail | Balustrade ¦ Handrail | lm | 20.4 | calculated | #NAME? | dxf_geometry: verandah_perimeter=20.40 m | #NAME? | MEDIUM
K03 | 50124 | 50124 - Stairs & Balustrades | Balustrade Post | Balustrade ¦ Post | nr | 17 | calculated | ceil(verandah_perimeter / 1.2 m) | derived from verandah_perimeter=20.40 m | ceil(perimeter / 1.2) | LOW

## Manual Review
Item No | Package Code | Item Display Name | Unit | Qty | Confidence | Status | Notes / Action Required
G01 | 50107 | Floor Panel ¦ 1.8kPa Standard Load | nr | 21 | LOW | inferred | MANUAL REVIEW REQUIRED. General pharmacy areas (waiting, consultation, staff, storage). 70% area estimate from building use. No FrameCAD floor tab available — obtain actual panel schedule from engineer. Panel dimensions assumed 600mm × 3600mm (2.16m² each).
G02 | 50107 | Floor Joist ¦ LGS C150, 1.8kPa Zone | lm | 100.8 | LOW | inferred | MANUAL REVIEW REQUIRED. General pharmacy areas (waiting, consultation, staff, storage). 70% area estimate from building use. No FrameCAD floor tab available — obtain actual panel schedule from engineer. Joist count at 450mm spacing across 7.2m span, 9.0m run.
G03 | 50107 | Floor Bearer ¦ 1.8kPa Zone, pair | nr | 3 | LOW | inferred | MANUAL REVIEW REQUIRED. General pharmacy areas (waiting, consultation, staff, storage). 70% area estimate from building use. No FrameCAD floor tab available — obtain actual panel schedule from engineer. Bearer pairs at 1800mm spacing. Verify from structural schedule.
G04 | 50107 | Floor Panel ¦ 4kPa High Load | nr | 9 | LOW | inferred | MANUAL REVIEW REQUIRED. Dispensary area with heavy shelving/equipment. 30% area estimate. Obtain actual panel schedule from FrameCAD engineer before ordering. Panel dimensions assumed 600mm × 3600mm (2.16m² each).
G05 | 50107 | Floor Joist ¦ LGS C150, 4kPa Zone | lm | 43.2 | LOW | inferred | MANUAL REVIEW REQUIRED. Dispensary area with heavy shelving/equipment. 30% area estimate. Obtain actual panel schedule from FrameCAD engineer before ordering. Joist count at 450mm spacing across 7.2m span, 9.0m run.
G06 | 50107 | Floor Bearer ¦ 4kPa Zone, pair | nr | 2 | LOW | inferred | MANUAL REVIEW REQUIRED. Dispensary area with heavy shelving/equipment. 30% area estimate. Obtain actual panel schedule from FrameCAD engineer before ordering. Bearer pairs at 1800mm spacing. Verify from structural schedule.
G07 | 50107 | FC Sheet Floor ¦ 18mm thk, 1200 x 2400 Sheet | sheets | 24 | LOW | calculated | MANUAL REVIEW REQUIRED. Sheet size assumed same as ceiling FC sheet (1.2×2.4). Adjust if different.
H02 | 50107 | Substructure ¦ Strip Footing Concrete Volume | m3 | 7.68 | LOW | calculated | MANUAL REVIEW REQUIRED. Strip footing assumed for steel floor frame bearing lines. Assumed 500 mm deep × 400 mm wide. Verify type and dimensions from structural drawings.
H04 | 50107 | Substructure ¦ Bulk Earthworks / Level (provisional) | m3 | 0 | LOW | placeholder | MANUAL REVIEW REQUIRED. Excavation volume cannot be derived from architectural documents.
H06 | 50107 | Substructure ¦ Strip Footing, Internal Bearing | m3 | 5.88 | LOW | calculated | MANUAL REVIEW REQUIRED. Assumed 500 mm deep × 400 mm wide. Verify.
H08 | 50107 | Substructure ¦ Pad Footing Concrete Volume | m3 | 5.145 | LOW | calculated | MANUAL REVIEW REQUIRED. Assumes 700×700×700 mm pads. Verify from structural engineer.
A12 | 50111 | Fixing ¦ 12G-14x20mm HEX Head, DP | boxes | 19 | MEDIUM | calculated | MANUAL REVIEW REQUIRED. Stud-to-track connections: 2300.4lm × 4.0 per m = ~9202 screws, 19 boxes (500/box). Density: 2 screws per stud end (top+bottom). Verify with FrameCAD connection schedule.
A13 | 50111 | Fixing ¦ 10G-24x40mm Countersunk, DP | boxes | 3 | MEDIUM | calculated | MANUAL REVIEW REQUIRED. Purlin-to-rafter / roof panel connections: 481.7lm × 3.0 per m = ~1445 screws, 3 boxes. Verify with FrameCAD connection report.
A14 | 50111 | Fixing ¦ 10G-14x16mm Wafer Head, DP | boxes | 7 | LOW | calculated | MANUAL REVIEW REQUIRED. Batten-to-purlin connections: 1385.3lm total batten × 2.5 per m = ~3463. Includes roof, wall, and ceiling batten zones from FrameCAD BOM. Verify zone scope before ordering.
A15 | 50111 | Fixing ¦ M12 x 75mm Sleeve Anchor (Pad Footings) | nr | 60 | MEDIUM | calculated | MANUAL REVIEW REQUIRED. 15 pad footings × 4 M12×75 anchors each (4-bolt base plate). Verify anchor embedment depth and edge distance from structural engineer.
A16 | 50111 | PH Bracket ¦ Post Holder (PHA/PHB/PHD) | nr | 28 | LOW | calculated | MANUAL REVIEW REQUIRED. Post holder brackets at column bases. Count estimated from IFC steel post lm. Verify bracket type (PHA/PHB/PHD) against post size and load from structural drawings.
A17 | 50111 | Accessories ¦ Triple Grip Connector (Pryda) | nr | 36 | LOW | calculated | MANUAL REVIEW REQUIRED. Roof-to-wall-plate cyclonic uplift connections at 1.2m centres along 42.4m eave line = 36 nr. Verify spacing and type from structural engineer (cyclone region requirement).
A18 | 50111 | Accessories ¦ Hold Down Washer, Cyclonic | nr | 60 | LOW | calculated | MANUAL REVIEW REQUIRED. Hold-down washers at post base connections. 15 pads × 4 = 60 nr. Verify washer specification (size, grade) from structural drawings.
A19 | 50111 | Accessories ¦ Fix Plate Connector, G350 | nr | 18 | LOW | calculated | MANUAL REVIEW REQUIRED. Fix plates at strap bracing termination points: 49.7lm × 0.35 = 18 nr. Verify against FrameCAD connection schedule.
A20 | 50111 | Accessories ¦ Strap Brace Tensioner | nr | 34 | LOW | calculated | MANUAL REVIEW REQUIRED. Strap termination anchors: 49.7lm ÷ 3m avg run = 17 runs × 2 ends. Verify strap count and anchor type from FrameCAD connection schedule.
A21 | 50111 | Accessories ¦ Grommet 35mm Dia | nr | 45 | LOW | inferred | MANUAL REVIEW REQUIRED. Cable/conduit grommets at LGS stud penetrations. 29.4m internal wall × 1.5 per m = 45 nr. Quantity depends on electrical/hydraulic layout. Verify from services drawings.
A22 | 50111 | Fixing ¦ Structural Fixings Remainder (PLACEHOLDER) | item | 0 | LOW | placeholder | MANUAL REVIEW REQUIRED. PLACEHOLDER for connection schedule items not derivable from member lm alone. Typical items: M10/M12/M16 hex bolts (hold-down posts), angle brackets (knee bracing, ridge connections), spring washers, nyloc nuts. Obtain FrameCAD connection report for full schedule. Reference BOQ includes 256+ individual fixing line items — this row represents residual scope.
B03 | 50112 | Roof Cladding ¦ Custom Orb Corrugated CGI Sheet | sheets | 49 | MEDIUM | calculated | MANUAL REVIEW REQUIRED. run=2.51m (area/eaves) + 150mm lap → select 3.0m stock Verify sheet length and profile from spec.
B13 | 50112 | Barge Cap ¦ Galvanised, lm | lm | 8.5 | LOW | calculated | MANUAL REVIEW REQUIRED.
B14 | 50112 | Barge End Cap ¦ Galvanised | nr | 2 | LOW | calculated | MANUAL REVIEW REQUIRED. 2 end caps per barge run (ridge peak and eaves)
K05 | 50113 | External Cladding ¦ FC Weatherboard | nr | 126 | MEDIUM | calculated | MANUAL REVIEW REQUIRED. Weatherboard: 200mm exposure, 4200mm stock length. Count includes 5% waste. Verify board profile and lap from spec.
K13 | 50113 | Substructure ¦ Site Preparation (Provisional) | item | 0 | LOW | placeholder | MANUAL REVIEW REQUIRED. Site preparation scope cannot be derived from drawings. Confirm with engineer.
D26 | 50114 | Window ¦ Louvre Blade, 1100mm Wide | nr | 64 | LOW | calculated | MANUAL REVIEW REQUIRED. Frame height 750 mm (config_default=750mm). 8 blades per frame at 100 mm pitch. Verify blade count and size from window schedule.
D29 | 50114 | Window ¦ Louvre Blade, 800mm Wide | nr | 16 | LOW | calculated | MANUAL REVIEW REQUIRED. Frame height 750 mm (config_default=750mm). 8 blades per frame at 100 mm pitch. Verify blade count and size from window schedule.
D32 | 50114 | Window ¦ Louvre Blade, 1800mm Wide | nr | 8 | LOW | calculated | MANUAL REVIEW REQUIRED. Frame height 750 mm (config_default=750mm). 8 blades per frame at 100 mm pitch. Verify blade count and size from window schedule.
D42 | 50114 | Window ¦ Fly Screen, 1100mm Wide | m2 | 6.48 | LOW | calculated | MANUAL REVIEW REQUIRED. Fly screen for louvre window WINDOW_LOUVRE_1100 (8 nr). Area: 1.08m × 0.750m = 0.810 m² each. Tropical building — all louvre openings require insect screening. Verify frame height from window schedule.
D43 | 50114 | Window ¦ Fly Screen, 800mm Wide | m2 | 1.2 | LOW | calculated | MANUAL REVIEW REQUIRED. Fly screen for louvre window WINDOW_LOUVRE_800 (2 nr). Area: 0.80m × 0.750m = 0.599 m² each. Tropical building — all louvre openings require insect screening. Verify frame height from window schedule.
D44 | 50114 | Window ¦ Fly Screen, 1800mm Wide | m2 | 1.39 | LOW | calculated | MANUAL REVIEW REQUIRED. Fly screen for louvre window WINDOW_LOUVRE_1800 (1 nr). Area: 1.85m × 0.750m = 1.385 m² each. Tropical building — all louvre openings require insect screening. Verify frame height from window schedule.
D45 | 50114 | Door ¦ Closer, Hydraulic | nr | 1 | MEDIUM | inferred | MANUAL REVIEW REQUIRED. Door closer inferred for pharmacy entrance doors. Marks: DOOR_90 (1 nr). Verify which doors require closers from door schedule and architect. Commercial pharmacy may require controlled entry.
E06 | 50115 | Internal Lining ¦ Waterproof Board / FC, Wet Area | sheets | 7 | LOW | inferred | MANUAL REVIEW REQUIRED. Wet area lining derived from room perimeter estimate. Verify room dimensions.
I01 | 50117 | Hydraulics ¦ Hand Basin | nr | 1 | LOW | inferred | MANUAL REVIEW REQUIRED. Inferred from room type 'pharmacy'.
I02 | 50117 | Hydraulics ¦ Tapware | set | 1 | LOW | inferred | MANUAL REVIEW REQUIRED. Inferred from room type 'pharmacy'.
I03 | 50117 | Services ¦ Cold Room / Refrigeration (PLACEHOLDER) | item | 1 | LOW | inferred | MANUAL REVIEW REQUIRED. Inferred from room type 'pharmacy'.
I04 | 50117 | Services ¦ Builder's Works, Electrical | item | 1 | LOW | inferred | MANUAL REVIEW REQUIRED. Inferred from room type 'pharmacy'.
I05 | 50117 | Services ¦ Builder's Works, Services | item | 1 | LOW | inferred | MANUAL REVIEW REQUIRED. Inferred from room type 'waiting'.
I06 | 50117 | Hydraulics ¦ Hand Basin | nr | 1 | LOW | inferred | MANUAL REVIEW REQUIRED. Inferred from room type 'consulting'.
I07 | 50117 | Hydraulics ¦ Tapware | set | 1 | LOW | inferred | MANUAL REVIEW REQUIRED. Inferred from room type 'consulting'.
I08 | 50117 | Hydraulics ¦ Builder's Works (Plumbing) | item | 1 | LOW | inferred | MANUAL REVIEW REQUIRED. Inferred from room type 'consulting'.
I09 | 50117 | Services ¦ Builder's Works, Electrical | item | 1 | LOW | inferred | MANUAL REVIEW REQUIRED. Inferred from room type 'office'.
I10 | 50117 | Hydraulics ¦ WC Pan (close-coupled) | nr | 1 | MEDIUM | inferred | MANUAL REVIEW REQUIRED. Inferred from room type 'toilet'.
I11 | 50117 | Hydraulics ¦ WC Cistern | nr | 1 | MEDIUM | inferred | MANUAL REVIEW REQUIRED. Inferred from room type 'toilet'.
I12 | 50117 | Hydraulics ¦ Hand Basin | nr | 1 | MEDIUM | inferred | MANUAL REVIEW REQUIRED. Inferred from room type 'toilet'.
I13 | 50117 | Hydraulics ¦ Tapware | set | 1 | MEDIUM | inferred | MANUAL REVIEW REQUIRED. Inferred from room type 'toilet'.
I14 | 50117 | FFE ¦ Mirror | nr | 1 | LOW | inferred | MANUAL REVIEW REQUIRED. Inferred from room type 'toilet'.
I15 | 50117 | FFE ¦ Toilet Roll Holder | nr | 1 | LOW | inferred | MANUAL REVIEW REQUIRED. Inferred from room type 'toilet'.
I16 | 50117 | FFE ¦ Towel Rail | nr | 1 | LOW | inferred | MANUAL REVIEW REQUIRED. Inferred from room type 'toilet'.
I17 | 50117 | Hydraulics ¦ Floor Waste | nr | 1 | MEDIUM | inferred | MANUAL REVIEW REQUIRED. Inferred from room type 'toilet'.
I18 | 50117 | Hydraulics ¦ Builder's Works (Plumbing) | item | 1 | MEDIUM | inferred | MANUAL REVIEW REQUIRED. Inferred from room type 'toilet'.
I19 | 50117 | Hydraulics ¦ WC Pan | m2 | 15.3 | LOW | inferred | MANUAL REVIEW REQUIRED. Inferred: perimeter (8.5 m) × 1800 mm splash-zone height. No finish schedule in source documents. Verify tile type, height, and area from architectural drawings. Deduct openings.
I20 | 50117 | Hydraulics ¦ Wet Area Waterproofing Membrane | m2 | 5.78 | MEDIUM | inferred | MANUAL REVIEW REQUIRED. Waterproofing: floor area + 150 mm upstand on walls for Toilet. Verify room dimensions and upstand height from architectural drawings.
I21 | 50117 | Services ¦ Builder's Works, Services | item | 1 | LOW | inferred | MANUAL REVIEW REQUIRED. Inferred from room type 'store'.
I22 | 50117 | Services ¦ Air Conditioning / Mechanical (PLACEHOLDER) | item | 0 | LOW | placeholder | MANUAL REVIEW REQUIRED. PLACEHOLDER. Commercial building in tropical climate likely requires split-system or cassette AC units. No mechanical schedule or equipment schedule in source documents. Obtain from mechanical engineer or building services consultant. Include: outdoor units, indoor units, refrigerant pipework, electrical supply, condensate drainage, ceiling penetrations.
I23 | 50117 | Electrical ¦ Exhaust Fan | item | 0 | LOW | placeholder | MANUAL REVIEW REQUIRED. PLACEHOLDER. BCA F4.6 requires mechanical exhaust in rooms without openable windows. Confirm exhaust fan type, ducting, and external discharge location from architectural drawings.
I24 | 50117 | Electrical ¦ Main Switchboard / Distribution Board | item | 1 | LOW | inferred | MANUAL REVIEW REQUIRED. 1 per building; adjust for sub-boards
I25 | 50117 | Hydraulics ¦ Main Water Meter / Stopcock | item | 1 | LOW | inferred | MANUAL REVIEW REQUIRED. Whole-building service allowance.
I26 | 50117 | Hydraulics ¦ Hot Water System | item | 1 | LOW | inferred | MANUAL REVIEW REQUIRED. only if not allocated to individual rooms
I27 | 50117 | Electrical ¦ Smoke Detector | nr | 3 | LOW | inferred | MANUAL REVIEW REQUIRED. 1 per 40 m² floor area (indicative)
J01 | 50124 | Stair ¦ Stringer | nr | 1 | LOW | inferred | MANUAL REVIEW REQUIRED. Entry stair — riser count estimated from raised floor height (~525mm). Verify from architectural drawings.
J02 | 50124 | Stair ¦ Tread | nr | 3 | LOW | inferred | MANUAL REVIEW REQUIRED.
J04 | 50124 | Balustrade ¦ Assembly | lm | 0.75 | LOW | calculated | MANUAL REVIEW REQUIRED. Verify length from architectural drawings.
J05 | 50124 | Balustrade ¦ Post | nr | 1 | LOW | calculated | MANUAL REVIEW REQUIRED. 1 post per 1.2 m spacing. Verify from balustrade schedule.
J06 | 50124 | Balustrade ¦ Assembly | m2 | 0.75 | LOW | inferred | MANUAL REVIEW REQUIRED. Infill height assumed 1.0 m. Adjust for guard height requirement (≥1.0 m at >1.0 m fall).
J07 | 50124 | Balustrade ¦ Handrail | lm | 0.75 | LOW | calculated | MANUAL REVIEW REQUIRED. Verify handrail length. Continuous rail both sides of flight where required by code.
J08 | 50124 | Access Ramp ¦ Surface, Concrete / Non-slip | m2 | 8.82 | LOW | inferred | MANUAL REVIEW REQUIRED. Access ramp: 1:14 gradient, stair: 3 risers × 175 mm = 525 mm → 7.35 m run × 1.2 m wide = 8.82 m². Verify need and exact dimensions from architectural drawings and BCA D3.3.
J09 | 50124 | Access Ramp ¦ (type by design) | lm | 14.7 | LOW | inferred | MANUAL REVIEW REQUIRED. Continuous handrails both sides of ramp. Verify height and spec from architectural drawings.
J10 | 50124 | Access Ramp ¦ Edge Kerb / Guard | lm | 14.7 | LOW | inferred | MANUAL REVIEW REQUIRED. Kerb guard (min 75 mm high) both sides. Verify from architectural drawings.

## QA Summary
QA SUMMARY REPORT
QUANTITY PROVENANCE
Total Items | 172
Measured | 20
Calculated | 106
Inferred | 41
Placeholder | 5
Manual Review | 71
CONFIDENCE BREAKDOWN
HIGH | 30 | 17.4%
MEDIUM | 75 | 43.6%
LOW | 67 | 39.0%
PACKAGE COMPLETENESS (V3 sections)
Package | Status | Items | Measured | Calculated | Inferred | Placeholder
structural_frame | OK | 7 | 7 | 0 | 0 | 0
roof_cladding | OK | 3 | 0 | 3 | 0 | 0
openings_doors | OK | 5 | 3 | 2 | 0 | 0
openings_windows | OK | 12 | 3 | 9 | 0 | 0
wall_lining_external | OK | 2 | 0 | 2 | 0 | 0
wall_lining_internal | OK | 3 | 0 | 3 | 0 | 0
ceiling_lining | OK | 5 | 0 | 5 | 0 | 0
finishes | OK | 4 | 0 | 4 | 0 | 0
floor_system | UNCONFIRMED | 8 | 0 | 2 | 6 | 0
footings | OK | 8 | 1 | 6 | 0 | 1
services | OK | 27 | 0 | 0 | 25 | 2
insulation | OK | 2 | 0 | 2 | 0 | 0
WARNINGS / ISSUES
Template contamination check: PASSED — no BOQ template quantities detected.

## Source Summary
SOURCE SUMMARY
Input Files
ANGAU PHARMACY 01_arch.dxf
Angau Pharmacy.ifc
Angau Pharmacy Summary.pdf
Quantity Status Breakdown by Source
building_type=pharmacy | 2
ceiling_area=64.80 | 1
config room_schedule | 2
derived | 11
derived from clip count | 1
derived from project_config | 1
derived from ramp run | 2
derived_steel_floor | 3
dxf_blocks | 45
dxf_geometry | 42
ext_walls | 1
floor_area=86.40 | 4
framecad_bom | 14
ifc_model | 3
no | 3
project_config | 13
project_config+dxf_geometry | 2
room | 2
room_schedule | 19
rooms=['Toilet'] | 1